## Aug 2025
Dealer ID | Dealer Name | Type of Implementation | Region | Configuration - Assigned | Go Live | Date of Completion | Configuration - User List | Configuration - BP | Configuration - Comments | Configuration - Status | Pre Go Live - Assigned to | Pre Go Live - Domain Updated | Pre Go Live - Set Up Check | Pre Go Live - Comments | Go Live Testing - Assigned To | Go Live Testing - Sample ADF | Go Live Testing - Inbound Email Test | Go Live Testing - Outbound Mail Test | Go Live Testing - Data Migration Test | Go Live Testing - Comments | Config team didn’t work on the store
1067 | Lewiston Auto Co., Inc. | Conquest | USA West and Central | Not Configured | 2025-08-01 | NA | NA | NA | Config team didn’t work on the store | Not Configured | NA | NA | NA | Didn’t Perform Pre Go Live | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live | EM asked for standard Config
6561 | Akins Chevrolet | Buy/Sell | USA East | Sujatha | 2025-08-04 | 2025-07-31 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues | CRM not enabled
6887 | Stoler Chevrolet Buick | Buy/Sell | USA East | Nanjunda | 2025-08-04 | 2025-07-28 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues | Copy Store
6433 | Brown's Volkswagen | Conquest | Canada | Nanjunda | 2025-08-05 | 2025-07-29 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6780 | John Kennedy Ford Mazda | Conquest | Mid Market | Nanjunda | 2025-08-05 | 2025-07-28 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6779 | John Kennedy Ford | Conquest | Mid Market | Sujatha | 2025-08-05 | 2025-07-09 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6781 | John Kennedy Ford Jenkintown | Conquest | Mid Market | Nanjunda | 2025-08-05 | 2025-07-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6782 | John Kennedy Ford Phoenixville | Conquest | Mid Market | Sujatha | 2025-08-05 | 2025-07-02 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6777 | John Kennedy Ford Lincoln Mazda Pottstown | Conquest | Mid Market | Nanjunda | 2025-08-05 | 2025-07-05 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6786 | John Kennedy Subaru Inc | Conquest | Mid Market | Nanjunda | 2025-08-05 | 2025-07-02 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6763 | Luv Toyota of Bradford | Conquest | USA East | Nanjunda | 2025-08-05 | 2025-06-24 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
1851 | Oremor of Glendale, LLC | Conquest | USA West and Central | Sujatha | 2025-08-05 | 2025-07-29 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
5809 | Ferrari of Salt Lake City | Conquest | NA | Not Configured | 2025-08-10 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
6719 | Ken Garff Mercedes | Conquest | NA | Not Configured | 2025-08-10 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
6721 | Ken Garff Volvo | Conquest | NA | Not Configured | 2025-08-10 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
1554 | Blade Chevrolet, Inc | Conquest | USA West and Central | Nanjunda | 2025-08-11 | 2025-05-30 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6753 | Wilson Toyota | Conquest | USA West and Central | Nanjunda | 2025-08-11 | 2025-06-11 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | Migration Issues
6527 | Fairway Chevrolet GMC | Conquest | USA East | Nanjunda | 2025-08-12 | 2025-06-23 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6438 | Fairway Ford | Conquest | USA East | Nanjunda | 2025-08-12 | 2025-07-07 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6769 | Liberty Chrysler Dodge Jeep Ram | Conquest | USA East | Nanjunda | 2025-08-12 | 2025-06-24 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
880 | NA Motorcars, Inc. | Conquest | USA West and Central | Not Configured | 2025-08-14 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6980 | Napleton Palatine Hyundai | Buy/Sell | USA East | Nanjunda | 2025-08-14 | 2025-08-11 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
6979 | Napleton Palatine Chevy | Buy/Sell | USA East | Nanjunda | 2025-08-14 | 2025-08-11 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
6535 | Naguabo Auto Toyota | Conquest | USA East | Nanjunda | 2025-08-18 | 2025-07-29 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6897 | Reydel Volkswagen of Freehold | New Point | USA East | Sujatha | 2025-08-18 | 2025-07-18 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No | No | No | No | Domain not verified, EM confirmed this has been taken live but actual usage will begin next week, as it is a new point.
6773 | Milton Martin Honda | Conquest | USA East | Nanjunda | 2025-08-19 | 2025-08-04 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6889 | Lethbridge Volkswagen | Conquest | Canada | Nanjunda | 2025-08-19 | 2025-08-05 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6928 | Maverick Motors DFW | New Point | USA West and Central | Not Configured | 2025-08-19 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6881 | ALM CDJR Perry | Conquest | Mid Market | Not Configured | 2025-08-19 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6829 | Paul Sherry Chrysler | Conquest | USA East | Sujatha | 2025-08-19 | 2025-08-11 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6880 | ALM Kia of Perry | Conquest | Mid Market | Not Configured | 2025-08-19 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6832 | Burt Watson GMC, LLC | Buy/Sell | USA East | Nanjunda | 2025-08-25 | 2025-07-31 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
1003 | Bush Auto Group, Inc. | Conquest | USA East | Sujatha | 2025-08-25 |  | No | No | CRM not enabled | NA | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6568 | Sewell Chevrolet GMC | Conquest | USA West and Central | Nanjunda | 2025-08-25 | 2025-07-01 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
2473 | Grubbs Acura of Tulsa | Conquest | Mid Market | Sujatha | 2025-08-26 | 2025-07-23 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | The communication templates caused an error in the process automation.
6747 | Gunther Clermont | New Point | USA East | Sujatha | 2025-08-26 | 2025-06-20 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6567 | Sewell BMW of the Permian Basin | Conquest | USA West and Central | Nanjunda | 2025-08-26 | 2025-07-01 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
6570 | Sewell Buick GMC Cadillac of Midland | Conquest | USA West and Central | Nanjunda | 2025-08-26 | 2025-07-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
6571 | Sewell Chrysler Dodge Jeep Ram | Conquest | USA West and Central | Nanjunda | 2025-08-26 | 2025-07-07 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
6566 | Sewell Ford Lincoln | Conquest | USA West and Central | Nanjunda | 2025-08-26 | 2025-07-01 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
6837 | Young Honda | Conquest | Mid Market | Nanjunda | 2025-08-26 | 2025-08-20 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
7006 | Clay Cooley Hyundai of Sherman | Buy/Sell | USA West and Central | Not Configured | 2025-08-27 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6858 | South Richmond Chrysler Dodge Jeep Ram | Buy/Sell | USA East | Nanjunda | 2025-08-29 | 2025-06-25 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues

## Sep 2025
Dealer ID | Dealer Name | Type of Implementation | Region | Configuration - Assigned | Go Live | Date of Completion | Configuration - User List | Configuration - BP | Configuration - Comments | Configuration - Status | Pre Go Live - Assigned to | Pre Go Live - Domain Updated | Pre Go Live - Set Up Check | Pre Go Live - Comments | Go Live Testing - Assigned To | Go Live Testing - Sample ADF | Go Live Testing - Inbound Email Test | Go Live Testing - Outbound Mail Test | Go Live Testing - Data Migration Test | Go Live Testing - Comments | Config team didn’t work on the store
6747 | Gunther Clermont | New Point | USA East | Sujatha | 2025-09-01 | 2025-06-20 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No | No | No | No Issues | The domain was not verified at the time of go-live, which prevented us from receiving ADF. The issue was resolved the following day. | EM asked for standard Config
2546 | Luxury and Imports Leavenworth | Conquest | USA West and Central | Not configured | 2025-09-01 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Nanjunda | No | No | No | No Issues | The domain was not updated during the go-live as it was pending from the dealer. It was updated later once received. | CRM not enabled
1571 | Cody Chevrolet Inc. | Conquest | USA East | Not configured | 2025-09-02 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | The configuration team did not work, as the data was pending. The task was later completed by the EM | Copy Store
6739 | Ferrari of Seattle | Conquest | USA West and Central | Not configured | 2025-09-02 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No | Template Issue was found Templates setups were not migrated- updated manully
6874 | Mike Fair GM Perth | New Point | Canada | Sujatha | 2025-09-02 | 2025-07-18 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | The configuration team did not work, as the data was pending. The task was later completed by the EM
6839 | Young Chrysler Jeep Dodge Ram Morgan | Conquest | Mid Market | Sujatha | 2025-09-02 | 2025-08-27 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6840 | Young Ford of Brigham City | Conquest | Mid Market | Sujatha | 2025-09-02 | 2025-08-27 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6837 | Young Honda | Conquest | Mid Market | Nanjunda | 2025-09-02 | 2025-08-20 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6836 | Young Used Center | Conquest | Mid Market | Sujatha | 2025-09-02 | 2025-08-27 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No | Template Issue was found Templates setups were not migrated- updated manully
6832 | Burt Watson GMC, LLC | Buy/Sell | USA East | Nanjunda | 2025-09-03 | 2025-07-31 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6862 | Courtesy Subaru | Conquest | USA West and Central | Not configured | 2025-09-03 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Account key and SNT were not updated- Waiting for input from the dealer. It has been update later
6831 | Chuck Anderson Ford | Conquest | USA West and Central | Not configured | 2025-09-03 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
1725 | Acura of Concord | Conquest | USA West and Central | Nanjunda | 2025-09-08 | 2025-09-04 | Yes | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | The configuration team did not work, as the data was pending. The task was later completed by the EM
5969 | Applewood Kia Langley | Conquest | Canada | Sujatha | 2025-09-09 | 2025-09-08 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
5731 | Applewood Kia Surrey | Conquest | Canada | Sujatha | 2025-09-09 | 2025-09-08 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6901 | Don Wood Chrysler Dodge Jeep | Conquest | USA East | Sujatha | 2025-09-09 | 2025-09-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6909 | Don Wood Ford Lincoln | Conquest | USA East | Sujatha | 2025-09-09 | 2025-09-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6892 | Don Wood Hyundai | New Point | USA East | Sujatha | 2025-09-09 | 2025-09-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6893 | Don Wood Toyota | New Point | USA East | Sujatha | 2025-09-09 | 2025-09-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6891 | Don Wood Chevrolet | Conquest | USA East | Sujatha | 2025-09-09 | 2025-09-05 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
6847 | Downtown Ford Sacramento | Conquest | Mid Market | Sujatha | 2025-09-09 | 2025-08-12 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Account key and SNT were not updated- Waiting for input from the dealer. It has been update later
6766 | Jamestown Honda | Conquest | USA East | Sujatha | 2025-09-09 | 2025-07-18 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6764 | Luv Toyota | Conquest | USA East | Sujatha | 2025-09-09 | 2025-07-21 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6860 | Mohawk Chevrolet | Conquest | USA East | Nanjunda | 2025-09-09 | 2025-08-07 | No | Yes | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Account key and SNT were not updated- Waiting for input from the dealer. It has been update later
6657 | Rosen Hyundai / Genesis Algonquin | Conquest | USA East | Sujatha | 2025-09-09 | 2025-07-09 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6658 | Rosen Hyundai Kenosha | Conquest | USA East | Nanjunda | 2025-09-09 | 2025-07-03 | No | Yes | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6859 | Ken Garff West Valley Chrysler Dodge Jeep Ram | Conquest | NA | Not configured | 2025-09-14 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | No Issues
6877 | Dave Kring Chevrolet Inc | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-08-12 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6765 | LUV Kia of Jamestown | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-07-08 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
1903 | Galleria Chevrolet | Conquest | USA West and Central | Not configured | 2025-09-16 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
2046 | Legacy Chevrolet GMC of Waxahachie | Buy/Sell | USA West and Central | Not configured | 2025-09-16 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
1770 | Principle Mississippi, Ltd | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-09-05 | No | Yes | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6762 | Porsche Centre Langley | Conquest | Canada | Not configured | 2025-09-16 | NA | No | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6825 | Porsche Centre Richmond | Conquest | Canada | Nanjunda | 2025-09-16 | 2025-07-05 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
1771 | Principle Volkswagen | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-07-18 | No | Yes | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6827 | Watford Ford Lincoln | Conquest | Canada | Nanjunda | 2025-09-16 | 2025-08-25 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
922 | Wind Gap Chevrolet | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-06-25 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No | Communication template were missing in prodcution Communication templates were blown out.
6883 | Ken Garff Hyundai Downtown | Conquest | NA | Not configured | 2025-09-21 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | No Issues
6907 | Ken Garff Hyundai Southtowne | Conquest | NA | Not configured | 2025-09-21 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | No Issues
6804 | Daniels Chevrolet Buick GMC | Conquest | USA East | Sujatha | 2025-09-23 | 2025-07-16 | Yes | Yes | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
1817 | Oremor of Temecula LX, LLC | Conquest | USA West and Central | Not configured | 2025-09-23 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
1816 | Oremor of Temecula, LLC | Conquest | USA West and Central | Not configured | 2025-09-23 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
6695 | Rosen Ford | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-08 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
6696 | Rosen Honda | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-08 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
6694 | Rosen Hyundai Greenfield | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-09 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
6692 | Rosen Kia Milwaukee | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-15 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
6700 | Rosen Nissan Milwaukee | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-14 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
6693 | Rosen Nissan of Madison | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-14 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
7061 | Carvana Chrysler Dodge Jeep Ram of Park Cities | Buy/Sell | USA West and Central | Sujatha | 2025-09-23 | 2025-09-19 | No | No | Copy store | Copy | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6900 | Subaru of Lethbridge | Conquest | Canada | Nanjunda | 2025-09-23 | 2025-07-21 | No | No | Copy store | Copy | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
6982 | MAG CDJR | Buy/Sell | USA West and Central | Not configured | 2025-09-26 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
6905 | Carvilla | Conquest | USA East | Nanjunda | 2025-09-29 | 2025-09-08 | No | No | EM asked for standard Config | Stnadard Configuration
5801 | Marthaler Honda | Conquest | USA West and Central | Sujatha | 2025-09-29 | 2025-09-25 | NA | NA | EM asked for standard Config | Stnadard Configuration
6904 | Autoplex Atlanta | Conquest | USA East | Nanjunda | 2025-09-29 | 2025-09-08 | No | No | EM asked for standard Config | Stnadard Configuration
6560 | Clark Nissan | Conquest | USA West and Central | Sujatha | 2025-09-30 | 2025-09-15 | No | No | EM asked for standard Config | Stnadard Configuration
1471 | Community HOL Automotive, LLC | Conquest | USA East | Sujatha | 2025-09-30 | 2025-07-03 | No | No | EM asked for standard Config | Stnadard Configuration
7018 | Diehl Chevrolet of North Hills | Buy/Sell | USA East | Not configured | 2025-09-26 | NA | NA | NA | Config team didn’t work on the store | Not Configured
6879 | Gunther Daytona | Conquest | USA East | Sujatha | 2025-09-30 | 2025-08-26 | No | No | Copy store | Copy
2181 | Medlin Hyundai | Conquest | USA East | Sujatha | 2025-09-30 | 2025-07-21 | No | No | EM asked for standard Config | Stnadard Configuration
2179 | Medlin Buick GMC Mazda | Conquest | USA East | Nanjunda | 2025-09-30 | 2025-07-18 | No | No | EM asked for standard Config | Stnadard Configuration
7055 | Neptune Motors LLC | Buy/Sell | USA East | Not configured | 2025-09-26 | NA | NA | NA | Config team didn’t work on the store | Not Configured
6800 | Stokes Kia | Conquest | Mid Market | Nanjunda | 2025-09-30 | 2025-09-04 | No | No | EM asked for standard Config | Stnadard Configuration

## Oct 2025
Dealer ID | Dealer Name | Type of Implementation | Region | Configuration - Assigned | Go Live | Date of Completion | Configuration - User List | Configuration - BP | Configuration - Comments | Configuration - Status | Pre Go Live - Assigned to | Pre Go Live - Domain Updated | Pre Go Live - Set Up Check | Pre Go Live - Comments | Go Live Testing - Assigned To | Go Live Testing - Sample ADF | Go Live Testing - Inbound Email Test | Go Live Testing - Outbound Mail Test | Go Live Testing - Data Migration Test | Go Live Testing - Comments | Config team didn’t work on the store
6982 | MAG CDJR | Buy/Sell | USA East | Handled by EM | 2025-10-01 | [15 empty] | EM asked for standard Config
6560 | Clark Nissan | Conquest | USA West and Central | Sujatha | 2025-10-07 | 2025-09-15 | NA | NA | EM asked for standard Config | Stnadard Configuration | [10 empty] | CRM not enabled
6916 | Eby Ford Lincoln | Conquest | USA East | Nanjunda | 2025-10-07 | 2025-09-15 | NA | NA | EM asked for standard Config | Stnadard Configuration | [10 empty] | Copy Store
6911 | Elco Chevrolet Cadillac | Conquest | USA West and Central | Nanjunda | 2025-10-07 | 2025-09-09 | NA | NA | EM asked for standard Config | Stnadard Configuration
2004 | Fresno Lexus | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-07
1595 | Pine Belt CDJR, INC | Conquest | USA West and Central | Yet to start | 2025-10-07
1593 | Pine Belt Ford | Conquest | USA West and Central | Yet to start | 2025-10-07
1596 | Pine Belt Imports | Conquest | USA West and Central | Yet to start | 2025-10-07
1597 | Pine Belt Imports of Brookhaven LLC | Conquest | USA West and Central | Yet to start | 2025-10-07
1594 | Pine Belt Motors, LLC. | Conquest | USA West and Central | Yet to start | 2025-10-07
1226 | Richmond Hill Hyundai | Conquest | Canada | Yet to start | 2025-10-07
1126 | Thornhill Hyundai | Conquest | Canada | Yet to start | 2025-10-07
6894 | Ken Garff Nissan of Orem | Conquest | NA | Not Under Ready For Configuration | 2025-10-12
6896 | Ken Garff Honda of Orem | Conquest | NA | Not Under Ready For Configuration | 2025-10-12
6895 | Ken Garff Volkswagen | Conquest | NA | Not Under Ready For Configuration | 2025-10-12
1794 | Centennial Imports, Inc. | Conquest | USA East | Not Under Ready For Configuration | 2025-10-13
1013 | Normandin CJDR | Conquest | USA West and Central | Yet to start | 2025-10-13
6647 | Lexus Carlsbad | Conquest | USA West and Central | Nanjunda | 2025-10-14 | 2025-08-04 | NA | NA | EM asked for standard Config | Stnadard Configuration
7010 | Liberty CDJR | New Point | USA East | Yet to start | 2025-10-14
6646 | Lexus Escondido | Conquest | USA West and Central | Nanjunda | 2025-10-14 | 2025-08-05 | NA | NA | EM asked for standard Config | Stnadard Configuration
2181 | Medlin Hyundai | Conquest | USA East | Sujatha | 2025-10-14 | 2025-07-21 | NA | NA | EM asked for standard Config | Stnadard Configuration
2179 | Medlin Buick GMC Mazda | Conquest | USA East | Nanjunda | 2025-10-14 | 2025-07-18 | NA | NA | EM asked for standard Config | Stnadard Configuration
2180 | Medlin Chevrolet | Conquest | USA East | Nanjunda | 2025-10-14 | 2025-09-25 | Yes | Yes | EM asked for standard Config | Stnadard Configuration
1768 | Nordic Imports II, Ltd. | Conquest | USA East | Yet to start | 2025-10-14
1994 | Mercedes - Benz of El Cajon | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-14
1767 | Performance of Mt. Moriah, Ltd. | Conquest | USA East | Yet to start | 2025-10-14
5811 | Irvine Acura | Buy/Sell | USA West and Central | Not Under Ready For Configuration | 2025-10-14
7073 | Ineos Grenadier of Irvine | Buy/Sell | Mid Market | Not Under Ready For Configuration | 2025-10-14
6562 | Hartwell Hereford | Conquest | United Kingdom | Not Under Ready For Configuration | 2025-10-15
7076 | Young Chrysler Dodge Jeep of Riverdale | Buy/Sell | Mid Market | Sujatha | 2025-10-21 | 2025-09-24 | NA | NA | Copy store | Copy
6988 | Bell and Bell Buick GMC | Conquest | Mid Market | Nanjunda | 2025-10-21 | 2025-09-24 | Yes | Yes | EM asked for standard Config | Stnadard Configuration
6940 | Gunther Coconut Creek | Conquest | USA East | Sujatha | 2025-10-21 | 2025-09-23 | NA | NA | Copy store | Copy
6939 | Gunther Delray Beach | Conquest | USA East | Sujatha | 2025-10-21 | 2025-09-23 | NA | NA | Copy store | Copy
6724 | Larson Cadillac | New Point | Mid Market | Sujatha | 2025-10-21 | 2025-06-10 | NA | NA | EM asked for standard Config | Stnadard Configuration
6723 | Larson Dodge | New Point | Mid Market | Sujatha | 2025-10-21 | 2025-06-13 | NA | NA | EM asked for standard Config | Stnadard Configuration
6725 | Porsche Tacoma | New Point | Mid Market | Sujatha | 2025-10-21 | 2025-06-17 | NA | NA | EM asked for standard Config | Stnadard Configuration
6726 | Larson Hyundai of Tacoma | New Point | Mid Market | Nanjunda | 2025-10-21 | 2025-06-09 | NA | NA | EM asked for standard Config | Stnadard Configuration
6727 | Mercedes - Benz of Tacoma | New Point | Mid Market | Nanjunda | 2025-10-21 | 2025-06-09 | NA | NA | EM asked for standard Config | Stnadard Configuration
6728 | Volkswagen of Tacoma | New Point | Mid Market | Nanjunda | 2025-10-21 | 2025-06-09 | NA | NA | EM asked for standard Config | Stnadard Configuration
6730 | Audi Tacoma | Conquest | Mid Market | Nanjunda | 2025-10-21 | 2025-06-10 | NA | NA | EM asked for standard Config | Stnadard Configuration
1763 | Oremor of Tustin, LLC | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-21
6729 | Toyota of Tacoma | New Point | Mid Market | Nanjunda | 2025-10-21 | 2025-06-20 | NA | NA | EM asked for standard Config | Stnadard Configuration
6720 | Ken Garff Porsche Lehi | Conquest | NA | Not Under Ready For Configuration | 2025-10-26
6722 | Ken Garff Audi Lehi | Conquest | NA | Not Under Ready For Configuration | 2025-10-26
965 | Paul Miller Ford, Inc. | Conquest | USA East | Not Under Ready For Configuration | 2025-10-27
6996 | Alpha One Ford | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-28
6974 | Baker City Auto Ranch | Conquest | Mid Market | Not Under Ready For Configuration | 2025-10-28
1471 | Community HOL Automotive, LLC | Conquest | USA East | Sujatha | 2025-10-28 | 2025-07-03 | NA | NA | EM asked for standard Config | Stnadard Configuration
6746 | Fallon Ford - Toyota | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-28
6978 | Folsom Buick GMC | Conquest | USA West and Central | Yet to start | 2025-10-28
6977 | Epic Chevrolet Cadillac | Conquest | USA West and Central | Yet to start | 2025-10-28
6976 | Mountain Home Auto Ranch | Conquest | Mid Market | Not Under Ready For Configuration | 2025-10-28
6975 | Stateline Auto Ranch Subaru | Conquest | Mid Market | Not Under Ready For Configuration | 2025-10-28
6973 | Skalnek Ford | Conquest | USA East | Not Under Ready For Configuration | 2025-10-28