## Sheet1
Store Name/ID | Go-Live Date | Testing Status | Testing Success Rate % | Sharepoint Folder Link
Porsche Centre Kelowna- 6553 | 2025-04-22 | Completed | 94.64 | END TO END TESTING Report - Porsche Centre Kelowna - 6553.pdf
Applewood Kia Surrey- 5731 | 2025-04-29 | Completed | 98.21 | END TO END TESTING Report - Applewood Kia Surrey- 5731-.pdf
Brookshire Hyundai- 2600 | 2025-04-29 | Completed | 96.64 | END TO END TESTING Report - Brookshire Hyundai - 2600.pdf
Eau Claire Ford- 6598 | 2025-04-29 | Completed | 98.21 | END TO END TESTING Report - Eau Claire Ford- 6598.pdf
Kelsey Chevrolet - IN- 6572 | 2025-04-29 | Completed | 98.21 | E2E Testing- Kelsey Chevrolet - IN- 6572 1.pdf
St Clair Automotive- 6605 | 2025-04-29 | Completed | 98.21 | E2E Testing- St Clair Automotive- 6605.pdf
Ford of Downtown Chicago- 6042 | 2024-10-28 | Completed | 98.21 | E2E Testing- Ford of Downtown Chicago- 6042.pdf
Anderson Chrysler Dodge Jeep Ram- 6557 | 2025-05-06 | Completed | 98.21 | Anderson Chrysler Dodge Jeep Ram - 6557 - Copy.pdf
Anderson Nissan Mazda- 6558 | 2025-05-06 | Completed | 98.21 | Anderson Nissan Mazda- 6558 (1).pdf
Anderson Toyota Lexus- 6559 | 2025-05-06 | Completed | 96.64 | Anderson Toyota Lexus- 6559 (1).pdf
Clark Nissan- 6560 | 2025-05-06 | Completed | 98.21 | Clark Nissan- 6560.pdf
Honda of Meridian- 6447 | 2025-05-06 | Completed | 98.21 | Honda of Meridian- 6447.pdf
Minooka Subaru- 6237 | 2025-05-06 | Completed | 98.21 | Minooka Subaru- 6237.pdf
Stapp Interstate Toyota- 6592 | 2025-05-06 | Completed | 98.21 | Stapp Interstate Toyota- 6592.pdf
Simms Chevrolet Co- 6596 | 2025-05-06 | Completed | 98.21 | Simms Chevrolet Co- 6596
Toyota of Puyallup- 6591 | 2025-05-13 | Completed | 92.85 | Toyota of Puyallup- 6591
Bridge City Chrysler Dodge Jeep- 6590 | 2025-05-13 | Completed | 96.21 | Bridge City Chrysler Dodge Jeep- 6590
Davis Chevrolet GMC Buick Claresholm- 6639 | 2025-05-13 | Completed | 96.21 | Davis Chevrolet GMC Buick Claresholm- 6639
Davis Chrysler Dodge Jeep Ram Ltd- 6588 | 2025-05-13 | Completed | 96.21 | Davis Chrysler Dodge Jeep Ram Ltd- 6588
Kicking Horse Ford- 6641 | 2025-05-13 | Completed | 94.64 | Kicking Horse Ford- 6641
Landmark Dodge Chrysler Jeep Ram of Morrow- 6595 | 2025-05-13 | Completed | 98.21 | Davis Chevrolet GMC Buick Claresholm- 6639
Athens Dodge Chrysler Jeep- 6594 | 2025-05-13 | Completed | 98.21 | Athens Dodge Chrysler Jeep- 6594
Gateway Chevrolet Cadillac - 6597 | 2025-05-13 | Completed | 96.42 | Gateway Chevrolet Cadillac- 6597
Polestar Kansas City- 6519 | 2025-05-19 | Completed | 92.85 | Polestar Kansas City- 6519.pdf
Beardmore Chevrolet, Inc.- 6580 | 2025-05-20 | Completed | 98.21 | Beardmore Chevrolet, Inc.- 6580
Beardmore Subaru-6581 | 2025-05-20 | Completed | 96.21 | Beardmore Subaru-6581
Beardmore Hyundai- 6582 | 2025-05-20 | Completed | 98.21 | Beardmore Subaru-6581
Sewell BMW of the Permian Basin- 6567 | 2025-05-20 | Completed |  | Sewell BMW of the Permian Basin- 6567
Sewell Buick GMC Cadillac of Midland- 6570 | 2025-05-20
Sewell Ford Lincoln- 6566 | 2025-05-20
Adventure Subaru LLC - 6656 | 2025-05-27 | Completed |  | Adventure Subaru LLC- 6656.pdf
Cox Chrysler Dodge Jeep Ram- 6643 | 2025-05-27 | Completed |  | Cox Chrysler Dodge Jeep Ram- 6643 (1).pdf
Cox Toyota- 6644 | 2025-05-27 | Completed |  | Cox Toyota- 6644
Fox Chevrolet of Rochester Hills, Inc- 6635 | 2025-05-27 | Completed |  | Fox Chevrolet of Rochester Hills, Inc- 6635
Fox Automotive Group Inc- 6636 | 2025-05-27 | Completed |  | Fox Automotive Group Inc- 6636
Bickford Ford- 6032 | 2025-06-10 | Completed |  | Bickford Ford- 6032
Lexus Escondido- 6646 | 2025-06-10 | Completed |  | Lexus Escondido- 6646
Lexus Carlsbad- 6647 | 2025-06-11 | Completed |  | Lexus Carlsbad- 6647
Grizzly Trail Motors- 6661 | 2025-06-17 | Completed |  | Grizzly Trail Motors- 6661
Lamborghini Houston- 6536 | 2025-06-17 | Completed |  | Lamborghini Houston- 6536
Porsche of Barrington- 6687 | 2025-06-17 | Completed |  | Porsche of Barrington- 6687
Motor Werks INFINITI- 6691 | 2025-06-17 | Completed |  | Motor Werks INFINITI- 6691
Westlock Motors Limited- 6660 | 2025-06-17 | Completed |  | Westlock Motors Limited- 6660
Rosen Honda- 6696 | 2025-06-24 | Completed |  | Rosen Honda.pdf
Rosen Hyundai Greenfield- 6694 | 2025-06-24 | Completed |  | Rosen Hyundai Greenfield- 6694
Acura of Columbus- 2407 | 2025-07-08 | Completed |  | Acura of Columbus- 2407
Marthaler Honda of Albert Lea- 5801 | 2025-07-22 | Completed |  | Marthaler Honda of Albert Lea- 5801
Butler Nissan - 6795 | 2025-08-12 | Completed |  | Butler Nissan- 6795
Porsche Centre Langley- 6762 | 2025-08-12 | Completed |  | Porsche Centre Langley- 6762
Volvo Cars Marin- 6845 | 2025-08-12 | Completed |  | Volvo Cars Marin- 6845
Carriage Kia of Alpharetta- 6745 | 2025-08-12 | Completed |  | Carriage Kia of Alpharetta- 6745
Carriage Kia of Woodstock- 2037 | 2025-08-12 | Completed |  | Carriage Kia of Woodstock- 2037
Nucar Automall of St Albans- 5947 | 2025-08-12 | Completed |  | Nucar Automall of St Albans- 5947
Carriage Used Cars Gainesville- 2039 | 2025-08-12 | Completed |  | Carriage Used Cars Gainesville- 2039
Butler Toyota- 6797 | 2025-08-19 | Completed |  | Butler Toyota- 6797
Toyota Sunnyvale- 6843 | 2025-08-19 | Completed |  | Toyota Sunnyvale- 6843
Butler Lexus- 6796 | 2025-08-19 | completed |  | Butler Lexus- 6796
Honda Milton Martin Honda- 6773 | 2025-08-19 | Completed |  | Honda Milton Martin Honda- 6773
ALM Kia of Perry- 6880 | 2025-08-19 | Completed |  | ALM Kia of Perry- 6880
ALM CDJR Perry- 6881 | 2025-08-19 | Completed |  | ALM CDJR Perry- 6881
Young Ford of Brigham City- 6840 | 2025-08-26 | Completed | 98.21 | Young Ford of Brigham City- 6840.pdf
Liberty Chrysler Dodge Jeep Ram- 6769 | 2025-08-12 | Completed |  | Liberty Chrysler Dodge Jeep Ram- 6769.pdf
Downtown Ford Sacramento- 6847 | 2025-08-19 | Completed |  | Downtown Ford Sacramento- 6847.pdf
Mercedes-Benz of Fairfield- 6846 | 2025-08-19 | Completed |  | Mercedes-Benz of Fairfield- 6846.pdf
Mercedes Benz of Midlothian - 6924 | 2025-08-26
Merccdes-Benz of Richmond - 6922 | 2025-08-26
Folsom Lake CDJR - 6784 | 2025-08-26
Grubbs Acura of Tulsa - 2473 | 2025-08-26
Young Chrysler Jeep Dodge Ram Morgan - 6839 | 2025-08-26
Stokes Volkswagon - 6801 | 2025-09-02 | Completed | 98.21 | Stokes Volkswagon- 6801.pdf
Stokes Chevrolet of Moncks Corner - 6799 | 2025-09-02 | Completed |  | Stokes Chevrolet of Moncks Corner - 6799
Stokes Honda North - 6803 |  | Completed |  | Stokes Honda North - 6803.pdf
Stokes Mazda - 6802 | 2025-09-02 | Completed |  | Stokes Mazda - 6802
Courtesy Subaru - 6862 |  | Completed |  | Courtesy Subaru- 6862.pdf
Chuck Anderson Ford - 6831 | 2025-09-03 | Completed |  | Chuck Anderson Ford - 6831
Don Wood Chevrolet- 6891 |  | Completed |  | Don Wood Chevrolet- 6891
Don Wood Toyota- 6893 |  | Completed |  | Don Wood Toyota- 6893
Scholfield Honda- 6499 | 2025-09-09 | Completed |  | Scholfield Honda- 6499.pdf
Butler Chrysler Dodge Jeep- 6885 | 2025-09-09 | Completed |  | Butler Chrysler Dodge Jeep- 6885.pdf
Valdosta Toyota- 6884 | 2025-09-09 | Completed |  | Valdosta Toyota- 6884.pdf
Don Wood Chrysler Dodge Jeep- 6901 | 2025-09-09 | Completed |  | orsce
Carvilla- 6905 | 2025-09-16 | Completed |  | Carvilla- 6905
Jamestown Honda- 6766 | 2025-09-09 | Completed |  | Jamestown Honda- 6766
LUV Kia of Jamestown- 6765 | 2025-09-16 | Completed |  | LUV Kia of Jamestown- 6765
Bob Grimm Chevrolet, Inc.- 6870 | 2025-09-16 | Completed |  | E2E Testing - Bob Grimm Chevrolet, Inc.- 6870.pdf
Gunther Volvo Cars Daytona Beach | 2025-09-23 | Completed |  | Gunther Volvo Cars Daytona Beach
Gunther VW Daytona Beach | 2025-09-23 | Completed |  | Gunther VW Daytona Beach
Nucar Toyota of Norwood- 5944 | 2025-09-30 | Completed |  | Nucar Toyota of Norwood- 5944
Subaru of Lethbridge- 6900 | 2025-09-23 | Completed |  | Subaru of Lethbridge- 6900.pdf
Brady Chrysler Dodge Jeep Ram- 6890 | 2025-09-30 | Completed |  | Brady Chrysler Dodge Jeep Ram- 6890.pdf
Nucar Chevrolet of Norwood- 5946 | 2025-09-30 | Completed |  | Nucar Chevrolet of Norwood- 5946
Nucar Hyundai of Norwood |  |  |  | Nucar Hyundai of Norwood- 5937
Nucar Lannan Chevrolet of Woburn- 5950 | 2025-09-30 | Completed | 96.42% | Nucar Lannan Chevrolet of Woburn- 5950.pdf
Nucar Honda West- 5949 | 2025-09-30 | Completed | 94.64% | Nucar Honda West- 5949.pdf
Nucar Lannan Chevrolet of Lowell- 5948 | 2025-09-30 | Completed | 94.64% | Nucar Lannan Chevrolet of Lowell- 5948.pdf
Nucar Volkswagen of Norwood- 5942 | 2025-09-30 | Completed | 96.42% | Nucar Volkswagen of Norwood- 5942.pdf
Nucar Honda of Norwood- 5940 | 2025-09-30 | Completed | 94.64% | Nucar Honda of Norwood- 5940.pdf
Nucar Honda of Norwood- 5940 | 2025-09-30 | Completed | 94.64% | Nucar Toyota South- 5945.pdf
Nucar NISSAN SOUTH- 5938 | 2025-09-30 | Completed |  | Nucar NISSAN SOUTH- 5938
Casa Chevrolet Cadillac of Prescott- 6926 | 2025-10-07 | Completed | 98.21% | Casa Chevrolet Cadillac of Prescott- 6926.xlsx
Elco Chevrolet Cadillac- 6911 | 2025-10-07 | Completed | 98.21% | Elco Chevrolet Cadillac- 6911.xlsx
Eby Ford Lincoln- 6916 | 2025-10-07 | Completed | 98.21% | Eby Ford Lincoln- 6916.xlsx
Sanborn Chevrolet- 6908 | 2025-10-07 | Completed | 98.21% | Sanborn Chevrolet- 6908.xlsx
The Luxury Collection Walnut Creek- 6943 | 2025-10-07 | Completed |  | The Luxury Collection Walnut Creek- 6943.xlsx
Stokes Hodges Ford- 6913 | 2025-10-07 | Completed | 98.21% | Stokes Hodges Ford- 6913.xlsx
Honda Cars of Aiken- 6914 | 2025-10-07 | Completed |  | Honda Cars of Aiken- 6914
Casa Nissan of Prescott | 2025-10-07 | Completed |  | Casa Nissan of Prescott
Ken Garff Nissan of Orem- 6894 | 2025-10-12 | Completed | 66.07% | Ken Garff Nissan of Orem- 6894.xlsx
Neptune Motors LLC- 7055 | 2025-09-30 | Completed |  | Neptune Motors LLC- 7055.xlsx
Diehl Chevrolet of North Hills- 7018 | 2025-09-30 | Completed |  | Diehl Chevrolet of North Hills- 7018.xlsx
MAG CDJR- 6982 | 2025-10-01 | Completed
Ken Garff Honda of Orem- 6896 | 2025-10-12 | Completed | 67.85% | Ken Garff Honda of Orem- 6896.xlsx
Butler Chevrolet | 2025-10-14 | Completed |  | Butler Chevrolet- 6933
Butler Honda | 2025-10-14 | Completed |  | Butler Honda- 6886
Casa Nissan of Prescott
[5 empty] | Store Name/ID | Go-Live Date | SIM Start Date | Signoffs Check
[5 empty] | MAG CDJR- 6982 | 2025-09-26 | 2025-09-19 | Not yet started
[5 empty] | Brady Chrysler Dodge Jeep Ram- 6890 | 2025-09-30 | 2025-09-23 | Completed
[5 empty] | LeMars Chevrolet GMC- 7044 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | DCD 1-HQ- 7063 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | DCD MA Parts Warehouse- 6882 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Diehl Chevrolet of North Hills- 7018 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Gunther Daytona- 6879 | 2025-09-30 | 2025-09-23 | Not yet started
[5 empty] | Neptune Motors LLC- 7055 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Chevrolet of Norwood- 5946 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Honda West- 5949 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Honda of Norwood- 5940 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Hyundai of Norwood- 5937 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Lannan Chevrolet of Lowell- 5948 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Lannan Chevrolet of Woburn- 5950 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar NISSAN SOUTH- 5938 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Nissan of Norwood- 5936 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Toyota South- 5945 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Toyota of Norwood- 5944 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Nucar Volkswagen of Norwood- 5942 | 2025-09-30 | 2025-09-23 | NA
[5 empty] | Westlock Motors Limited 2- 6989 | 2025-09-30 | 2025-09-23 | NA
25.95 | 52.95 | 78.95 | 111.88 | 131.95 | 155.95 | 1900-06-29 22:48 | 233.95 | 265
306.88 | 333.95 | 361.95 | 389.95 | 397.88 | 428.88 | 1901-06-02 21:07 | 589.88 | 630.95
668.88 | 701.88 | 734.88 | 767.95 | 800.95 | 827.88 | 1902-05-09 22:48 | 927.95 | 961.88
994.88 | 1026.88 | 1058.88 | 1090.88 | 1122.88 | 1154.88 | 1903-03-31 21:07 | 1250.95 | 1282.95
1314.95 | 1346.95 | 1378.95 | 1410.95 | 1442.95 | 1474.95 | 1904-02-15 21:07 | 1571.88 | 1603.88
1635.88 | 1667.88 | 1699.88 | 1731.95 | 1763.95 | 1795.95 | 1904-12-31 22:48 | 1891.95 | 1923.95
1955.95 | 1988.88 | 2020.88 | 2052.88 | 2084.88 | 2116.88 | 1905-11-17 21:07 | 2212.88 | 2244.95
2276.95 | 2308.95 | 2340.95 | 2372.95 | 2404.95 | 2436.95 | 1906-10-04 21:07 | 2533.88 | 2565.88
2597.88 | 2629.88 | 2661.88 | 2693.88 | 2725.95 | 2757.95 | 1907-08-20 22:48 | 2853.95 | 2885.95
2942.88 | 2974.88 | 3006.95 | 3039.88 | 3071.88 | 3103.95 | 1908-08-01 21:07 | 3200.95 | 3233.88
3265.88 | 3297.95 | 3329.95 | 3362.88 | 3394.95 | 3426.95 | 1909-06-20 21:07 | 3523.95 | 3556.88
3588.95 | 3620.95 | 3653.88 | 3685.95 | 3717.95 | 3750.88 | 1910-05-09 22:48 | 3847.88 | 3879.95
3944.88 | 3976.95 | 4009.88 | 4041.95 | 4074.88 | 4106.95 | 1911-05-01 22:48 | 4204.95 | 4237.88
4269.95 | 4302.95 | 4335.88 | 4367.95 | 4400.88 | 4432.95 | 1912-03-22 22:48 | 4530.95 | 4563.88
4595.95 | 4628.88 | 4661.88 | 4693.95 | 4726.88 | 4758.95 | 1913-02-11 21:07 | 4856.95 | 4889.88
4961.95 | 4994.95 | 5027.95 | 5060.88 | 5093.88 | 5126.88 | 1914-02-14 21:07 | 5224.95 | 5257.95
5290.88 | 5323.88 | 5356.88 | 5389.88 | 5421.95 | 5454.95 | 1915-01-08 22:48 | 5553.88 | 5586.88
5619.88 | 5651.95 | 5684.95 | 5717.95 | 5750.88 | 5783.88 | 1915-12-03 21:07 | 5881.95 | 5914.95

## Stores Checklist
Dealership Name | Go-Live Date | Region | Size | Type of Implementation | SIM Start Date | Week Count | Config Check | Signoffs Check | Assignee | Testing Status | Comments
Bell Motor Cars- 6228 | 2025-01-21 | USA East | S | Conquest | 2025-01-14 | 3 | Completed | Completed | Herold | Completed
Ford of Hibbing- 6210 | 2025-01-21 | USA West and Central | XS | Conquest | 2025-01-14 | 3 | Completed | Completed | Vishal C | Completed
Puente Hills Toyota- 6208 | 2025-01-21 | USA West and Central | L | Conquest | 2025-01-14 | 3 | Completed | Completed | Vishal C | Completed
MEDLIN HYUNDAI- 2181 | 2025-01-21 | USA East | XS | Conquest | 2025-01-14 | 3 | Completed | Completed | Herold | Completed
Medlin Buick GMC Mazda- 2179 | 2025-01-21 | USA East | XS | Conquest | 2025-01-14 | 3 | Completed | Completed | Divya | Completed
Medlin Chevrolet- 2180 | 2025-01-21 | USA East | XS | Conquest | 2025-01-14 | 3 | Completed | Completed | Herold | Completed
Stratton Chevrolet- 6209 | 2025-01-21 | USA East | XS | Conquest | 2025-01-14 | 3 | Completed | Completed | Divya | Completed
Alpine Buick GMC Littleton- 6212 | 2025-01-28 | USA West and Central | S | Conquest | 2025-01-21 | 4 | Completed | Completed | Herold | Completed
Alpine Buick GMC South Inc- 6213 | 2025-01-28 | USA West and Central | S | Conquest | 2025-01-21 | 4 | Completed | Pending | Vishal C | Completed | Retail setups signoffs are not completed , Can go ahead with testing as per pod specialist
Alpine Ford- 6217 | 2025-01-28 | USA West and Central | S | Conquest | 2025-01-21 | 4 | Completed | Pending | Herold | Completed | Retail setups signoffs are not completed , Service sigoffs are done but not uploaded,Can go ahead with testing as per pod specialist
Alpine Nissan of Denver- 6215 | 2025-01-28 | USA West and Central | S | Conquest | 2025-01-21 | 4 | Completed | Completed | Herold | Completed
Infiniti of Denver- 6227 | 2025-01-28 | USA West and Central | S | Conquest | 2025-01-21 | 4 | Completed | Pending | Divya | Completed | Accounting and Retail Signoffs are not done,Can go ahead with testing as per pod specialist
Jaguar Land Rover Treasure Coast- 6234 | 2025-01-28 | USA East | S | Conquest | 2025-01-21 | 4 | Completed | Pending | Vishal C | Completed | Accounting and Retail Signoffs are not done
Palmetto57 Nissan- 6235 | 2025-01-28 | USA East | M | Conquest | 2025-01-21 | 4 | Completed | Completed | Herold | Completed
Palmetto57 Volkswagen- 6236 | 2025-01-28 | USA East | S | Conquest | 2025-01-21 | 4 | Completed | Completed | Herold | Completed | Accounting changes are made by EM
California Motors Trade - Norco- 6563 | 2025-02-04 | USA West and Central | XS | Conquest | 2025-01-28 | 5 | Pending | Pending | NA | Unable To Complete | No update from EM
Cook Ford- 6231 | 2025-02-04 | USA West and Central | S | Conquest | 2025-01-28 | 5 | Completed | Pending | Herold | Completed | Signoffs are not complete ,Can go ahead with testing as per pod specialist .
Don Larson Ford- 6429 | 2025-02-04 | USA West and Central | S | Conquest | 2025-01-28 | 5 | Completed | Pending | Herold | Completed | Signoffs are not complete ,Can go ahead with testing as per pod specialist .
Honor Buick Gmc- 6434 | 2025-02-04 | USA West and Central | S | Conquest | 2025-01-28 | 5 | Completed | Pending | Vishal C | Completed | Signoffs are not complete ,Can go ahead with testing as per pod specialist .
Brooklyn CJDR- 6226 | 2025-02-04 | USA East | M | Conquest | 2025-01-28 | 5 | Completed | Pending | Divya | Completed | Signoffs are not complete ,Can go ahead with testing as per pod specialist .
Strong Volkswagen- 6431 | 2025-02-04 | USA West and Central | M | Conquest | 2025-01-28 | 5 | Completed | Pending | Divya | Completed | Signoffs are not complete ,Can go ahead with testing as per pod specialist .
Tom Gill Buick GMC- 6461 | 2025-02-03 | USA East | XS | Buy/Sell | 2025-01-27 | 5 | Pending | Pending | NA | Unable To Complete | Accounting Config is not completed , Waiting for the update from EM - Task has been marked complete
Davis GMC Buick- 6201 | 2025-02-11 | Canada | M | Conquest | 2025-02-04 | 6 | Completed | Pending | Vishal C | Completed
Hemet CDJR- 6486 | 2025-02-11 | USA West and Central | S | Conquest | 2025-02-04 | 6 | Pending | Pending | NA | Unable To Complete | As advised by Bradley, store will not be worked by Config Team
Karl Flammer Ford Inc- 6205 | 2025-02-11 | USA East | M | Conquest | 2025-02-04 | 6 | Completed | Pending | Vishal C | Completed
Lake Elsinore Chrysler Dodge Jeep Ram- 6487 | 2025-02-11 | USA West and Central | S | Conquest | 2025-02-04 | 6 | Pending | Pending | NA | Unable To Complete | As advised by Bradley, store will not be worked by Config Team
Madera Chevrolet- 6241 | 2025-02-11 | USA West and Central | S | Conquest | 2025-02-04 | 6 | Completed | Pending | Divya | Completed
Moore Cadillac Richmond- 6200 | 2025-02-11 | USA East | S | Conquest | 2025-02-04 | 6 | Completed | Pending | Herold | Completed
Moore Cadillac Chantilly- 6199 | 2025-02-11 | USA East | S | Conquest | 2025-02-04 | 6 | Completed | Pending | Herold | Completed
Pedder Nissan- 6495 | 2025-02-11 | USA West and Central | S | Conquest | 2025-02-04 | 6 | Pending | Pending | NA | Unable To Complete | As advised by Bradley, store will not be worked by Config Team
Raceway Nissan- 6496 | 2025-02-11 | USA West and Central | S | Conquest | 2025-02-04 | 6 | Pending | Pending | NA | Unable To Complete | As advised by Bradley, store will not be worked by Config Team
Temecula Nissan- 6485 | 2025-02-11 | USA West and Central | S | Conquest | 2025-02-04 | 6 | Pending | Pending | NA | Unable To Complete | As advised by Bradley, store will not be worked by Config Team
Volume Chevrolet- 6432 | 2025-02-11 | USA East | XS | Conquest | 2025-02-04 | 6 | Completed | Pending | Divya | Completed
Cadillac Marin- 6445 | 2025-02-18 | Mid Market | XS | Conquest | 2025-02-11 | 7 | Completed | Completed | Herold | Completed
Toyota Marin- 6446 | 2025-02-18 | Mid Market | L | Conquest | 2025-02-11 | 7 | Completed | Completed | Herold | Completed
Quantrell Cadillac- 6448 | 2025-02-18 | USA East | M | Conquest | 2025-02-11 | 7 | Completed | Pending | Divya | Completed
Northgate Ford Lincoln- 6436 | 2025-02-18 | USA East | XS | Conquest | 2025-02-11 | 7 | Completed | Pending | Divya | Completed
Hyundai on Perryville- 6440 | 2025-02-18 | USA East | XS | Conquest | 2025-02-11 | 7 | Completed | Completed | Divya | Completed
Grand Rapids Chevrolet GMC- 6443 | 2025-02-18 | USA West and Central | XS | Conquest | 2025-02-11 | 7 | Completed | Pending | Herold | Completed
Anderson Rock River- 6439 | 2025-02-18 | USA East | S | Conquest | 2025-02-11 | 7 | Completed | Pending | Vishal C | Completed
Porsche of North Houston- 6452 | 2025-02-25 | Mid Market | S | Conquest | 2025-02-18 | 8 | Completed | Pending | Divya | Completed
Automotores del Este- 2089 | 2025-02-25 | USA East | XS | Conquest | 2025-02-18 | 8 | Completed | Completed | Vishal C | Completed
Fairway Chevrolet GMC- 6527 | 2025-02-25 | USA East | XS | Conquest | 2025-02-18 | 8 | Completed | Pending | Herold | Completed
Fairway Ford- 6438 | 2025-02-25 | USA East | S | Conquest | 2025-02-18 | 8 | Completed | Completed | Herold | Completed
Fajardo Ford- 2088 | 2025-02-25 | USA East | XS | Conquest | 2025-02-18 | 8 | Completed | Completed | Herold | Completed | Reatils signoffs are not completed
Sauers Buick GMC- 1608 | 2025-02-25 | USA East | XS | Conquest | 2025-02-18 | 8 | Completed | Pending | Divya | Unable to Complete
Eagle Ridge GM- 6531 | 2025-03-03 | Canada | S | Conquest | 2025-02-24 | 9 | Completed | Completed | Herold | Completed
Ken Stoepel Ford- 6517 | 2025-03-04 | USA West and Central | M | Conquest | 2025-02-25 | 9 | Completed | Pending | Divya | Completed
Audi of Boise- 6427 | 2025-03-04 | USA West and Central | S | Conquest | 2025-02-25 | 9 | Completed | Completed | Herold | Completed
Burtness Chevrolet - Orfordville- 6450 | 2025-03-04 | USA West and Central | XS | Conquest | 2025-02-25 | 9 | Completed |  | Vishal C | Completed
Burtness Chevrolet Buick GMC - CDJR- 6455 | 2025-03-04 | USA West and Central | XS | Conquest | 2025-02-25 | 9 | Completed | Completed | Divya | Completed
Boise Volkswagen- 6426 | 2025-03-04 | USA West and Central | S | Conquest | 2025-02-25 | 9 | Completed | Pending | Herold | Unable To Complete
Ken Garff Ford Ft Collins- 6489 | 2025-03-10 | Enterprise | L | Conquest | 2025-03-03 | 10 | Completed | Pending | Divya | Unable to Complete | EM is working on the store
Ken Garff Ford Greeley- 6488 | 2025-03-10 | Enterprise | L | Conquest | 2025-03-03 | 10 | Completed | Pending | Divya | Unable to Complete | EM is working on the store
Haddad Toyota- 6058 | 2025-03-11 | Mid Market | M | Conquest | 2025-03-04 | 10 | Completed | Completed | Divya | Completed
Haddad Hyundai- 6045 | 2025-03-11 | Mid Market | S | Conquest | 2025-03-04 | 10 | Completed | Completed | Vishal C | Completed
Haddad Subaru- 6044 | 2025-03-11 | Mid Market | S | Conquest | 2025-03-04 | 10 | Completed | Completed | Vishal C | Completed
Friendly Chevrolet- 6541 | 2025-03-18 | USA West and Central | L | Conquest | 2025-03-11 | 11 | Completed | Completed | Herold | Completed
Kinley Ford- 6473 | 2025-03-18 | USA East | M | Conquest | 2025-03-11 | 11 | Completed | Completed | Herold | Completed | Retrail and accounting signoffs are pending - Accounting is not completed
Kinley Chevrolet- 6474 | 2025-03-18 | USA East | S | Conquest | 2025-03-11 | 11 | Completed | Completed | Herold | Completed
Kinley Ford of Lancaster- 6475 | 2025-03-18 | USA East | S | Conquest | 2025-03-11 | 11 | Completed | Completed | Divya | Completed
Generation Kia- 6239 | 2025-03-18 | USA East | XS | Conquest | 2025-03-11 | 11 | Completed | Completed | Vishal C | Completed | NA
Generation Buick GMC- 6240 | 2025-03-18 | USA East | XS | Conquest | 2025-03-11 | 11 | Pending | Completed | Herold | Completed
Napleton's Countryside Mazda- 6514 | 2025-03-18 | Mid Market | XS | Conquest | 2025-03-11 | 11 | Completed | Completed | Herold | Completed | Testing Not required as they are copied stores
Napleton's Honda of Morton Grove- 6515 | 2025-03-18 | Mid Market | S | Conquest | 2025-03-11 | 11 | Completed | Completed | Divya | Completed | Testing Not required as they are copied stores
Napleton's Oak Lawn Mazda- 6516 | 2025-03-18 | Mid Market | XS | Conquest | 2025-03-11 | 11 | Completed | Completed | Vishal C | Completed | Testing Not required as they are copied stores
Napleton's Palatine Subaru- 6513 | 2025-03-18 | Mid Market | XS | Conquest | 2025-03-11 | 11 | Completed | Completed | Divya | Completed | Testing Not required as they are copied stores
North Country Chevrolet GMC- 6472 | 2025-03-18 | USA East | XS | Conquest | 2025-03-11 | 11 | Completed | Completed | Divya | Completed
Casa Nissan- 6506 | 2025-03-25 | Mid Market | M | Conquest | 2025-03-18 | 12 | Completed | Completed | Vishal C | Completed
Casa Buick GMC- 6507 | 2025-03-25 | Mid Market | M | Conquest | 2025-03-18 | 12 | Completed | Completed | Herold | Completed
Casa Ford Lincoln- 6505 | 2025-03-25 | Mid Market | XXL | Conquest | 2025-03-18 | 12 | Completed | Completed | Divya | Completed
Scoggin-Dickey Chevrolet Buick- 6460 | 2025-03-25 | USA West and Central | M | Conquest | 2025-03-18 | 12 | Completed | Completed | Vishal C | Completed
Casa Ford Las Cruces- 6509 | 2025-03-25 | Mid Market | S | Conquest | 2025-03-18 | 12 | Completed | Completed | Herold | Completed
Casa Honda Las Cruces- 6510 | 2025-03-25 | Mid Market | S | Conquest | 2025-03-18 | 12 | Completed | Completed | Herold | Completed
Casa Hyundai Las Cruces- 6511 | 2025-03-25 | Mid Market | XS | Conquest | 2025-03-18 | 12 | Completed | Completed | Herold | Completed
Casa Kia- 6508 | 2025-03-25 | Mid Market | S | Conquest | 2025-03-18 | 12 | Completed | Completed | Divya | Completed
Casa Mazda Las Cruces- 6512 | 2025-03-25 | Mid Market | XS | Conquest | 2025-03-18 | 12 | Completed | Completed | Divya | Completed
Scoggin Dickey Chrysler Dodge Jeep Ram- 6453 | 2025-03-25 | USA West and Central | S | Conquest | 2025-03-18 | 12 | Completed | Completed | Vishal C | Completed
Scoggin Dickey ADI- 6454 | 2025-03-25 | USA West and Central | S | Conquest | 2025-03-18 | 12 | Completed | Completed | Vishal C | Completed
Ferrari of Newport Beach- 6502 | 2025-04-01 | USA West and Central | S | Conquest | 2025-03-25 | 13 | Completed | Completed | Herold | Completed
Ferrari of San Diego- 6503 | 2025-04-01 | USA West and Central | XS | Conquest | 2025-03-25 | 13 | Completed | Completed | Herold | Completed
Brown's Volkswagen- 6433 | 2025-04-01 | Canada | S | Conquest | 2025-03-25 | 13 | Completed | Completed | Vishal C | Completed
Haddad Subaru of St. Albans- 6046 | 2025-04-01 | Mid Market | S | Conquest | 2025-03-25 | 13 | Completed | Completed | Vishal C | Completed
McSweeney CDJR Clanton- 6577 | 2025-04-01 | USA West and Central | S | Conquest | 2025-03-25 | 13 | Completed | Completed | Divya | Completed
Koons Toyota Westminster- 6586 | 2025-04-06 | Enterprise | M | Conquest | 2025-03-30 | 14 | Pending | Pending | NA | Unable To Complete | Unapproved
Scoggin Dickey ADI- 6454 | 2025-03-25 | USA West and Central | S | Conquest | 2025-03-18 | 12 | Completed | Pending | NA | Unable to Complete
Estherville Chevrolet GMC- 6583 | 2025-04-08 | USA West and Central | XS | Conquest | 2025-04-01 | 14 | Completed | Completed | Lokesh | Completed
Henry Brown Buick GMC- 6522 | 2025-04-08 | USA West and Central | XXL | Conquest | 2025-04-01 | 14 | Completed | Completed | Vishal C | Completed
HB Custom- 6523 | 2025-04-08 | USA West and Central | S | Conquest | 2025-04-01 | 14 | Completed | Completed | Vishal C | Completed
Hutcheson Ford- 6529 | 2025-04-08 | USA West and Central | S | Conquest | 2025-04-01 | 14 | Completed | Completed | Lokesh | Completed
Jerry's Chevrolet Inc- 6525 | 2025-04-08 | USA East | L | Conquest | 2025-04-01 | 14 | Completed | Completed | Herold | Completed
Jerry's Toyota- 6524 | 2025-04-08 | USA East | L | Conquest | 2025-04-01 | 14 | Completed | Completed | Herold | Completed
Key Buick GMC- 6584 | 2025-04-08 | Mid Market | S | Conquest | 2025-04-01 | 14 | Completed | Completed | Amaresh | Completed
Key Hyundai- 6575 | 2025-04-08 | Mid Market | S | Conquest | 2025-04-01 | 14 | Pending | Pending | NA | Unable To Complete | No Task
North Florida Lincoln- 6576 | 2025-04-08 | Mid Market | S | Conquest | 2025-04-01 | 14 | Completed | Completed | Divya | Completed
Spirit Lake Ford CDJR- 6573 | 2025-04-08 | USA West and Central | XS | Conquest | 2025-04-01 | 14 | Completed | Completed | Amaresh | Completed
Estherville Chevrolet GMC- 6583 | 2025-04-08 | USA West and Central | XS | Conquest | 2025-04-01 | 14 | Completed | Completed | Divya | Completed
Henry Brown Buick GMC- 6522 | 2025-04-08 | USA West and Central | XXL | Conquest | 2025-04-01 | 14 | Completed | Completed | Herold | Completed
HB Custom- 6523 | 2025-04-08 | USA West and Central | S | Conquest | 2025-04-01 | 14 | Completed | Completed | Vishal C | Completed
Jerry's Toyota- 6524 | 2025-04-08 | USA East | L | Conquest | 2025-04-01 | 14 | Completed | Completed | Herold | Completed
Ken Garff Kia Bell Road- 6493 | 2025-04-13 | Enterprise | M | Conquest | 2025-04-06 | 15 | Pending | Pending | NA | Unable To Complete | Config not done
Ken Garff Hyundai Surprise- 6494 | 2025-04-13 | Enterprise | S | Conquest | 2025-04-06 | 15 | Pending | Pending | NA | Unable To Complete | Config not done
Davis Chevrolet Brooks- 6534 | 2025-04-15 | Canada | XS | Conquest | 2025-04-08 | 15 | Completed | Completed | Divya | Completed
Davis Chevrolet GMC Buick Airdrie- 6533 | 2025-04-15 | Canada | M | Conquest | 2025-04-08 | 15 | Completed | Completed | Herold | Completed
Davis GMC Buick Medicine Hat- 6532 | 2025-04-15 | Canada | S | Conquest | 2025-04-08 | 15 | Completed | Completed | Vishal C | Completed
Landmark Chrysler Dodge Jeep Ram Fiat Of Atlanta- 6554 | 2025-04-15 | USA East | S | Conquest | 2025-04-08 | 15 | Completed | Completed | Herold | Completed
Napleton Ford of Oak Lawn- 6540 | 2025-04-15 | Mid Market | S | Conquest | 2025-04-08 | 15 | Completed | Completed | Herold | Completed | COPY Stores No GL mapping available
Napleton's Palatine Mazda- 6538 | 2025-04-15 | Mid Market | XS | Conquest | 2025-04-08 | 15 | Completed | Completed | Herold | Completed | COPY Stores No GL mapping available
Napleton's Schaumburg Buick GMC- 6547 | 2025-04-15 | Mid Market | S | Conquest | 2025-04-08 | 15 | Pending | Pending | Vishal C | Unable To Complete | COPY Stores No GL mapping available
Napleton's Schaumburg Mazda- 6548 | 2025-04-15 | Mid Market | XS | Conquest | 2025-04-08 | 15 | Pending | Pending | Vishal C | Unable To Complete | COPY Stores No GL mapping available
Napleton's Schaumburg Subaru- 6539 | 2025-04-15 | Mid Market | XS | Conquest | 2025-04-08 | 15 | Pending | Pending | Vishal C | Unable To Complete | COPY Stores No GL mapping available
Koons Toyota Annapolis- 6626 | 2025-04-20 | Enterprise | M | Conquest | 2025-04-13 | 16 | Pending | Pending | NA | Unable To Complete | Config not done
Koons Chevrolet Buick GMC Clarksville- 6625 | 2025-04-20 | Enterprise | M | Conquest | 2025-04-13 | 16 | Pending | Pending | NA | Unable To Complete | Config not done
Ken Garff Kia Avondale- 6492 | 2025-04-22 | Enterprise | M | Conquest | 2025-04-15 | 16 | Pending | Pending | NA | Unable To Complete | Config not done
Ken Garff Volkswagen Gilbert- 6491 | 2025-04-22 | Enterprise | M | Conquest | 2025-04-15 | 16 | Pending | Pending | NA | Unable To Complete | Config not done
Mike Fair Chevrolet Buick GMC Cadillac- 6544 | 2025-04-22 | Canada | S | Conquest | 2025-04-15 | 16 | Completed | Completed | Vishal C | Completed
Porsche Centre Kelowna- 6553 | 2025-04-22 | Canada | S | Conquest | 2025-04-15 | 16 | Pending | Pending | NA | Unable To Complete | Accounting not completed
Koons Toyota Easton- 6606 | 2025-04-27 | Enterprise | M | Conquest | 2025-04-20 | 17 | Pending | Pending | NA | Unable To Complete | Config not done
Chesrown Chevrolet Buick GMC- 6552 | 2025-04-29 | USA East | S | Conquest | 2025-04-22 | 17 | Completed | Completed | Herold | Completed
Porsche Centre Kelowna- 6553 | 2025-04-22 | Canada | S | Conquest | 2025-04-15 | 16 | Completed | Completed | Herold | Completed
Applewood Kia Surrey- 5731 | 2025-04-29 | Canada | S | Conquest | 2025-04-22 | 17 | Pending | Pending | Herold | Completed
Eau Claire Ford Lincoln Quick Lane- 6598 | 2025-04-29 | USA West and Central | S | Conquest | 2025-04-22 | 17 | Pending | Pending | Herold | Completed
Kelsey Chevrolet - IN- 6572 | 2025-04-29 | USA East | S | Conquest | 2025-04-22 | 17 | Completed | Completed | Divya | Completed
Naguabo Auto Toyota- 6535 | 2025-04-29 | USA East | XS | Conquest | 2025-04-22 | 17 | Pending | Pending | Divya | Unable To Complete | Accounting not completed
St Clair Automotive- 6605 | 2025-04-29 | USA East | S | Conquest | 2025-04-22 | 17 | Completed | Completed | Vishal C | Completed
Ford of Downtown Chicago- 6042 | 2025-09-16 | Mid Market | S | Buy/Sell | 2025-09-09 | 37 | Completed | Completed | Divya | Completed | Request - Elizabeth Tipps
Naguabo Auto Toyota- 6535 | 2025-04-29 | USA East | XS | Conquest | 2025-04-22 | 17 | Pending | Pending | NA | Unable To Complete | chart of acc not loaded, go live date moved
Koons Ford Woodbridge- 6607 | 2025-05-04 | Enterprise | M | Conquest | 2025-04-27 | 18 | Pending | Pending | NA | Unable To Complete | Config not done
Anderson Chrysler Dodge Jeep Ram- 6557 | 2025-05-06 | USA East | S | Conquest | 2025-04-29 | 18 | Completed | Completed | Divya | Completed
Anderson Nissan Mazda- 6558 | 2025-05-06 | USA East | XS | Conquest | 2025-04-29 | 18 | Completed | Completed | Divya | Completed
Anderson Toyota Lexus- 6559 | 2025-05-06 | USA East | S | Conquest | 2025-04-29 | 18 | Completed | Completed | Divya | Completed
Clark Nissan- 6560 | 2025-05-06 | USA West and Central | S | Conquest | 2025-04-29 | 18 | Completed | Completed | Divya | Completed
Honda of Meridian- 6447 | 2025-05-06 | Mid Market | S | Conquest | 2025-04-29 | 18 | Completed | Completed | Divya | Completed
Jeremy Hodge Chevrolet GMC- 6627 | 2025-05-06 | Mid Market | XS | Conquest | 2025-04-29 | 18 | Pending | Pending | NA | Unable To Complete | Accounting not completed
Minooka Subaru - customer- 6237 | 2025-05-06 | Mid Market | S | Conquest | 2025-04-29 | 18 | Completed | Completed | Divya | Completed
Petro Nissan- 6640 | 2025-05-06 | USA East | XS | Conquest | 2025-04-29 | 18 | Pending | Pending | NA | Unable To Complete | Config not done
Simms Chevrolet Co- 6596 | 2025-05-06 | USA East | S | Conquest | 2025-04-29 | 18 | Completed | Completed | Divya | Completed
Stapp Interstate Toyota- 6592 | 2025-05-06 | USA West and Central | M | Conquest | 2025-04-29 | 18 | Completed | Completed | Divya | Completed
Koons Toyota Arlington- 6585 | 2025-05-11 | Enterprise | M | Conquest | 2025-05-04 | 19 | Pending | Pending | Divya | Unable To Complete | Config not done by our team
Toyota of Puyallup- 6591 | 2025-05-13 | USA West and Central | XL | Conquest | 2025-05-06 | 19 | Completed | Completed | Divya | Completed
Koons Collision Repair Center- 6615 | 2025-05-11 | Enterprise | M | Conquest | 2025-05-04 | 19 | Pending | Pending | Divya | Unable To Complete | Config not done
Bridge City Chrysler Dodge Jeep- 6590 | 2025-05-13 | Canada | S | Conquest | 2025-05-06 | 19 | Completed | Completed | Divya | Completed
Davis Chevrolet GMC Buick Claresholm- 6639 | 2025-05-13 | Canada | XS | Conquest | 2025-05-06 | 19 | Completed | Completed | Divya | Completed
Davis Chrysler Dodge Jeep Ram Ltd- 6588 | 2025-05-13 | Canada | XS | Conquest | 2025-05-06 | 19 | Completed | Completed | Divya | Completed
Davis Wholesale- 6589 | 2025-05-13 | Canada | XS | Conquest | 2025-05-06 | 19 | Pending | Pending | Divya | Unable To Complete | Parts not loaded, config not done by our team
Gateway Chevrolet Cadillac- 6597 | 2025-05-13 | Mid Market | XL | Conquest | 2025-05-06 | 19 | Completed | Completed | Divya | Completed
Kicking Horse Ford- 6641 | 2025-05-13 | Canada | XS | Conquest | 2025-05-06 | 19 | Completed | Completed | Divya | Completed
Athens Dodge Chrysler Jeep- 6595 | 2025-05-13 | USA East | L | Conquest | 2025-05-06 | 19 | Completed | Completed | Divya | Completed
Athens Dodge Chrysler Jeep Ram- 6594 | 2025-05-13 | USA East | L | Conquest | 2025-05-06 | 19 | Completed | Completed | Divya | Completed | Athens Dodge Chrysler Jeep- 6594
Koons Hyundai Woodbridge- 6614 | 2025-05-13 | Enterprise | M | Conquest | 2025-05-06 | 19 | Pending | Pending | NA | Unable To Complete | Config not done
Polestar Kansas City- 6519 | 2025-05-19 | USA East | XS | New Point | 2025-05-12 | 20 | Completed | Completed | Divya | Completed
Beardmore Chevrolet, Inc.- 6580 | 2025-05-20 | USA West and Central | S | Conquest | 2025-05-13 | 20 | Completed | Completed | Divya | Completed
Beardmore Subaru, Inc.- 6581 | 2025-05-20 | USA West and Central | S | Conquest | 2025-05-13 | 20 | Completed | Completed | Divya | Completed
Beardmore Hyundai- 6582 | 2025-05-20 | USA West and Central | XS | Conquest | 2025-05-13 | 20 | Completed | Completed | Divya | Completed
Sewell BMW of the Permian Basin- 6567 | 2025-05-20 | USA West and Central | XS | Conquest | 2025-05-13 | 20 | Completed | Completed | Divya | Completed
Sewell Buick GMC Cadillac of Midland- 6570 | 2025-05-20 | USA West and Central | S | Conquest | 2025-05-13 | 20 | Completed | Completed | Sunil | Completed
Sewell Ford Lincoln- 6566 | 2025-05-20 | USA West and Central | XXL | Conquest | 2025-05-13 | 20 | Completed | Completed | Sunil | Completed
Adventure Subaru LLC- 6656 | 2025-05-27 | USA East | S | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
Applewood Kia Langley- 5969 | 2025-05-27 | Canada | S | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
Cox Chrysler Dodge Jeep Ram- 6643 | 2025-05-27 | USA East | S | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
Cox Toyota- 6644 | 2025-05-27 | USA East | M | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
Fox Chevrolet of Rochester Hills, Inc- 6635 | 2025-05-27 | Mid Market | S | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
Fox Automotive Group Inc- 6636 | 2025-05-27 | Mid Market | XS | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
San Leandro Chrysler Jeep Dodge Ram- 6653 | 2025-05-27 | USA West and Central | S | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
Stockton Hyundai- 6654 | 2025-05-27 | USA West and Central | XS | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
Sienna Karma- 6734 | 2025-05-27 | USA East | XS | Conquest | 2025-05-20 | 21 | Completed | Completed | Divya | Completed
Koons Tysons Toyota- 6230 | 2025-06-09 | USA East | M | Conquest | 2025-06-02 | 23 | Completed | Completed | Divya | Completed
Bickford Ford- 6032 | 2025-06-10 | USA West and Central | M | Conquest | 2025-06-03 | 23 | Completed | Completed | Divya | Completed
Lexus Escondido- 6646 | 2025-06-10 | USA West and Central | M | Conquest | 2025-06-03 | 23 | Completed | Completed | Divya | Completed
Carlsbad Collision Center LLC- 6645 | 2025-06-10 | USA West and Central | S | Conquest | 2025-06-03 | 23 | Pending | Pending | Divya | Unable To Complete
Lexus Carlsbad- 6647 | 2025-06-10 | USA West and Central | S | Conquest | 2025-06-03 | 23 | Completed | Completed | Divya | Completed
Porsche Centre Calgary- 6655 | 2025-06-10 | Canada | S | Conquest | 2025-06-03 | 23 | Completed | Completed | Divya | Completed
Toyota Carlsbad- 6648 | 2025-06-10 | USA West and Central | XXL | Conquest | 2025-06-03 | 23 | Completed | Completed | Divya | Completed
Rosen Hyundai / Genesis Algonquin- 6657 | 2025-06-10 | USA East | S | Conquest | 2025-06-03 | 23 | Completed | Completed | Divya | Completed
Rosen Hyundai Kenosha- 6658 | 2025-06-10 | USA East | XS | Conquest | 2025-06-03 | 23 | Completed | Completed | Divya | Completed
Koons Chevrolet White Marsh- 6612 | 2025-06-16 | Enterprise | M | Conquest | 2025-06-09 | 24 | Completed | Completed | Divya | Completed
Koons Volvo Cars White Marsh- 6617 | 2025-06-16 | Enterprise | M | Conquest | 2025-06-09 | 24 | Completed | Completed | Divya | Completed
Grizzly Trail Motors- 6661 | 2025-06-17 | Canada | XS | Conquest | 2025-06-10 | 24 | Completed | Completed | Divya | Completed
Lamborghini Houston- 6536 | 2025-06-17 | Mid Market | XS | Conquest | 2025-06-10 | 24 | Completed | Completed | Divya | Completed
Porsche of Barrington- 6687 | 2025-06-17 | USA East | S | Conquest | 2025-06-10 | 24 | Completed | Completed | Divya | Completed
Motor Werks Management Company- 6788 | 2025-06-17 | USA East | XS | Conquest | 2025-06-10 | 24 | Pending | Pending | NA | Unable To Complete | Acc is pending
Motor Werks Cadillac- 6688 | 2025-06-17 | USA East | S | Conquest | 2025-06-10 | 24 | Pending | Pending | NA | Unable To Complete | Acc is pending
BMW of Barrington- 6689 | 2025-06-17 | USA East | S | Conquest | 2025-06-10 | 24 | Completed | Completed | Divya | Completed
Mercedes-Benz of Barrington- 6752 | 2025-06-17 | USA East | M | Conquest | 2025-06-10 | 24 | Completed | Completed | Divya | Completed
Motor Werks Honda- 6690 | 2025-06-17 | USA East | S | Conquest | 2025-06-10 | 24 | Completed | Completed | Divya | Completed
Motor Werks INFINITI- 6691 | 2025-06-17 | USA East | S | Conquest | 2025-06-10 | 24 | Completed | Completed | Divya | Completed
Westlock Motors Limited- 6660 | 2025-06-17 | Canada | S | Conquest | 2025-06-10 | 24 | Completed | Completed | Divya | Completed
Rosen Honda- 6696 | 2025-07-08 | Mid Market | S | Conquest | 2025-07-01 | 27 | Completed | Completed | Divya | Completed
Rosen Hyundai Greenfield- 6694 | 2025-07-08 | Mid Market | S | Conquest | 2025-07-01 | 27 | Completed | Completed | Divya | Completed
McCluskey Chevrolet- 6669 | 2025-07-08 | USA East | XXL | Conquest | 2025-07-01 | 27 | Completed | Completed | Divya | Completed
Acura of Columbus- 2407 | 2025-07-08 | Mid Market | XS | Conquest | 2025-07-01 | 27 | Completed | Completed | Divya | Completed
BMW of Columbus- 6811 | 2025-07-08 | Mid Market | XS | Conquest | 2025-07-01 | 27 | Completed | Completed | Divya | Completed
Marthaler Honda- 5801 | 2025-07-22 | USA West and Central | XS | Conquest | 2025-07-15 | 29 | Completed | Completed | Divya | Completed
Carriage Kia of Alpharetta- 6745 | 2025-08-12 | Mid Market | S | Conquest | 2025-08-05 | 32 | Completed | Completed | Amaresh | Completed
Carriage Kia of Woodstock- 2037 | 2025-08-12 | Mid Market | S | Conquest | 2025-08-05 | 32 | Completed | Completed | Amaresh | Completed
Carriage Used Cars Gainesville- 2039 | 2025-08-12 | Mid Market | S | Conquest | 2025-08-05 | 32 | Completed | Completed | Sujatha | Completed
Porsche Centre Langley- 6762 | 2025-08-12 | Canada | S | Conquest | 2025-08-05 | 32 | Completed | Completed | Divya | Completed
Porsche Centre Richmond- 6825 | 2025-08-12 | Canada | S | Conquest | 2025-08-05 | 32 | Completed | Completed | Amaresh | Completed
Volvo Cars Marin- 6845 | 2025-08-12 | Mid Market | XS | Conquest | 2025-08-05 | 32 | Completed | Completed | Divya | Completed
Butler Nissan- 6795 | 2025-08-19 | Mid Market | XS | Conquest | 2025-08-12 | 33 | Completed | Completed | Divya | Completed
Jaguar Land Rover Marin- 6848 | 2025-08-19 | Mid Market | S | Conquest | 2025-08-12 | 33 | Completed | Completed | Lokesh | Completed
Nucar Automall of St Albans- 5947 | 2025-08-12 | Mid Market | XS | Conquest | 2025-08-05 | 32 | Completed | Completed | Sujatha | Completed
Butler Toyota- 6797 | 2025-08-19 | Mid Market | M | Conquest | 2025-08-12 | 33 | Completed | Completed | Sujatha | Completed
Paul Sherry Chrysler- 6829 | 2025-08-19 | USA East | XS | Conquest | 2025-08-12 | 33 | Completed | Completed | Lokesh | Completed
Liberty Chrysler Dodge Jeep Ram- 6769 | 2025-08-12 | USA East | L | Conquest | 2025-08-05 | 32 | Completed | Completed | Sujatha | Completed
Alfa Romeo Stuart- 6868 | 2025-08-12 | Enterprise | XS | Conquest | 2025-08-05 | 32 | Pending | Pending | NA | Unable To Complete | GLAM is pending
Polestar Marin- 6844 | 2025-08-12 | Mid Market | XS | Conquest | 2025-08-05 | 32 | Pending | Pending | NA | Unable To Complete | Repair order error issue while adding customer details
Oakes Kia 2- 6824 | 2025-09-01 | USA East | XS | Buy/Sell | 2025-08-25 | 35 | Pending | Pending | NA | Unable To Complete | Glam Not configured
Milton Martin Honda- 6773 | 2025-08-19 | USA East | M | Conquest | 2025-08-12 | 33 | Completed | Completed | Divya | Completed
Butler Lexus- 6796 | 2025-08-19 | Mid Market | S | Conquest | 2025-08-12 | 33 | Completed | Completed | Nanjunda | Completed
Downtown Ford Sacramento- 6847 | 2025-08-19 | Mid Market | L | Conquest | 2025-08-12 | 33 | Completed | Completed | Sujatha | Completed
Mercedes-Benz of Fairfield- 6846 | 2025-08-19 | Mid Market | M | Conquest | 2025-08-12 | 33 | Completed | Completed | Sujatha | Completed
Toyota Sunnyvale- 6843 | 2025-08-19 | Mid Market | XL | Conquest | 2025-08-12 | 33 | Completed | Completed | Divya | Completed
ALM CDJR Perry- 6881 | 2025-08-19 | Mid Market | XS | Conquest | 2025-08-12 | 33 | Completed | Completed | Divya | Completed
ALM Kia of Perry- 6880 | 2025-08-19 | Mid Market | XS | Conquest | 2025-08-12 | 33 | Completed | Completed | Divya | Completed
Folsom Lake CDJR- 6784 | 2025-08-26 | USA West and Central | S | Conquest | 2025-08-19 | 34 | Completed | Completed | Lokesh | Completed
Grubbs Acura of Tulsa- 2473 | 2025-08-26 | Mid Market | XS | Conquest | 2025-08-19 | 34 | Completed | Completed | Lokesh | Completed
Young Chrysler Jeep Dodge Ram Morgan- 6839 | 2025-08-26 | Mid Market | S | Conquest | 2025-08-19 | 34 | Completed | Completed | Divya | Completed
Young Ford of Brigham City- 6840 | 2025-08-26 | Mid Market | S | Conquest | 2025-08-19 | 34 | Completed | Completed | Sujatha | Completed
Young Honda- 6837 | 2025-08-26 | Mid Market | XS | Conquest | 2025-08-19 | 34 | Pending | Pending | NA | Unable To Complete | https://tap.tekioncloud.com/support/tickets?ticketId=1454138Parts are locked, Need user code from Admin
Young Automotive- 6838 | 2025-08-26 | Mid Market | M | Conquest | 2025-08-19 | 34 | Pending | Pending | NA | Unable To Complete | Parts are locked, Need user code from Admin
Gunther Clermont- 6747 | 2025-09-01 | USA East | S | New Point | 2025-08-25 | 35 | Pending | Pending | NA | Unable To Complete | Parts are locked, Need user code from Admin
Gunther Clermont- 6747 | 2025-09-02 | Canada | S | New Point | 2025-08-26 | 35 | Pending | Pending | NA | Unable To Complete | Configration pending
Stokes Volkswagon- 6801 | 2025-09-02 | Mid Market | XS | Conquest | 2025-08-26 | 35 | Completed | Completed | Nanjunda | Completed
Stokes Kia- 6800 | 2025-09-02 | Mid Market | XS | Conquest | 2025-08-26 | 35 | Pending | Pending | NA | Unable To Complete | GLAM is pending
Stokes Chevrolet of Moncks Corner- 6799 | 2025-09-02 | Mid Market | XS | Conquest | 2025-08-26 | 35 | Completed | Completed | Divya | Completed
Stokes Honda North- 6803 | 2025-09-02 | Mid Market | M | Conquest | 2025-08-26 | 35 | Completed | Completed | Amaresh | Completed
Stokes Mazda- 6802 | 2025-09-02 | Mid Market | XS | Conquest | 2025-08-26 | 35 | Completed | Completed | Divya | Completed
Courtesy Subaru- 6862 | 2025-09-03 | USA West and Central | S | Conquest | 2025-08-27 | 35 | Completed | Completed | Nanjunda | Completed
Chuck Anderson Ford- 6831 | 2025-09-03 | USA West and Central | XS | Conquest | 2025-08-27 | 35 | Completed | Completed | Divya | Completed
Butler Chrysler Dodge Jeep- 6885 | 2025-09-09 | Mid Market | S | Conquest | 2025-09-02 | 36 | Completed | Completed | Amaresh | Completed
Don Wood Ford Lincoln- 6909 | 2025-09-09 | USA East | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Divya | Completed
Don Wood Chrysler Dodge Jeep- 6901 | 2025-09-09 | USA East | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Sujatha | Completed
Don Wood Toyota- 6893 | 2025-09-09 | USA East | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Divya | Completed
Don Wood Hyundai- 6892 | 2025-09-09 | USA East | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Lokesh | Completed
Don Wood Chevrolet- 6891 | 2025-09-09 | USA East | M | Conquest | 2025-09-02 | 36 | Completed | Completed | Divya | Completed
Jamestown Honda- 6766 | 2025-09-09 | USA East | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Divya | Completed
Luv Toyota- 6764 | 2025-09-09 | USA East | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Lokesh | Completed
Infiniti Stuart- 6545 | 2025-09-09 | Enterprise | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Amaresh | Completed | MURGADO - Enterprise. The empty testing sheet has been updated with comments indicating that testing for the enterprise was not performed, as per the update.
Bentley Jacksonville- 6872 | 2025-09-09 | Enterprise | S | Conquest | 2025-09-02 | 36 | Completed | Completed | Divya | Completed | MURGADO - Enterprise. The empty testing sheet has been updated with comments indicating that testing for the enterprise was not performed, as per the update.
Audi Stuart- 6865 | 2025-09-09 | Enterprise | S | Conquest | 2025-09-02 | 36 | Completed | Completed | Amaresh | Completed | MURGADO - Enterprise. The empty testing sheet has been updated with comments indicating that testing for the enterprise was not performed, as per the update.
Maserati Jacksonville- 6869 | 2025-09-09 | Enterprise | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Divya | Completed | MURGADO - Enterprise. The empty testing sheet has been updated with comments indicating that testing for the enterprise was not performed, as per the update.
Alfa Romeo Stuart- 6868 | 2025-09-09 | Enterprise | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Divya | Completed | MURGADO - Enterprise. The empty testing sheet has been updated with comments indicating that testing for the enterprise was not performed, as per the update.
Porsche Centre Richmond- 6825 | 2025-09-09 | Canada | S | Conquest | 2025-09-02 | 36 | Completed | Completed | Divya | Completed
Mohawk Chevrolet- 6860 | 2025-09-09 | USA East | L | Conquest | 2025-09-02 | 36 | Completed | Completed | Nanjunda | Completed
Bentley Edison- 6866 | 2025-09-09 | Enterprise | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Lokesh | Completed
Scholfield Honda- 6499 | 2025-09-09 | USA West and Central | L | Conquest | 2025-09-02 | 36 | Completed | Completed | Amaresh | Completed
Valdosta Toyota- 6884 | 2025-09-09 | Mid Market | S | Conquest | 2025-09-02 | 36 | Completed | Completed | Amaresh | Completed
Ferrari of Central New Jersey- 6867 | 2025-09-09 | Enterprise | XS | Conquest | 2025-09-02 | 36 | Completed | Completed | Amaresh | Completed
Carvilla- 6905 | 2025-09-16 | USA East | XS | Conquest | 2025-09-09 | 37 | Completed | Completed | Divya | Completed | 98.75
Bob Grimm Chevrolet, Inc.- 6870 | 2025-09-16 | USA East | S | Conquest | 2025-09-09 | 37 | Completed | Completed | Amaresh | Completed | 93.25
Dave Kring Chevrolet Inc- 6877 | 2025-09-16 | USA East | S | Conquest | 2025-09-09 | 37 | Completed | Completed | Lokesh | Completed
Honda of Westborough- 6932 | 2025-09-16 | Mid Market | S | Conquest | 2025-09-09 | 37 | Completed | Completed | Nanjunda | Completed | 98.75
LUV Kia of Jamestown- 6765 | 2025-09-16 | USA East | XS | Conquest | 2025-09-09 | 37 | Completed | Completed | Divya | Completed | 98.75
Porsche Centre Langley- 6762 | 2025-09-16 | Canada | S | Conquest | 2025-09-09 | 37 | Completed | Completed | Divya | Completed | 98.75
Autoplex Atlanta- 6904 | 2025-09-16 | USA East | XS | Conquest | 2025-09-09 | 37 | Completed | Completed | Amaresh | Completed | 93.25
Watford Ford Lincoln- 6827 | 2025-09-16 | Canada | S | Conquest | 2025-09-09 | 37 | Pending | Pending | NA | Unable To Complete | 74.5Completed (GLAM Issue)
Gunther Daytona- 6879 | 2025-09-23 | USA East | S | Conquest | 2025-09-16 | 38 | Completed | Completed | Divya | Completed | 96% AR statement download fail and F&I Products non availablity for Gunther Daytona - 6879
Honda of Downtown Chicago- 6946 | 2025-09-23 | Enterprise | S | Conquest | 2025-09-16 | 38 | Completed | Completed | Sujatha | Completed | Honda of Downtown Chicago - 6946 - failed cause of no configuration, MURGADO
Volkswagen Downtown Chicago- 6947 | 2025-09-23 | Enterprise | S | Conquest | 2025-09-16 | 38 | Completed | Completed | Amaresh | Completed | Volkswagen Downtown Chicago - 6947 - failed cause of no configuration, MURGADO
Acura Highland Park- 2408 | 2025-09-23 | Enterprise | S | Conquest | 2025-09-16 | 38 | Completed | Completed | Lokesh | Completed | Acura Highland Park - 2408 - failed cause of no configuration, MURGADO
Honda Libertyville- 6923 | 2025-09-23 | Enterprise | S | Conquest | 2025-09-16 | 38 | Completed | Completed | Divya | Completed | Honda Libertyville - 6923 - failed cause of no configuration, MURGADO
Subaru of Lethbridge- 6900 | 2025-09-23 | Canada | XS | Conquest | 2025-09-16 | 38 | Completed | Completed | Nanjunda | Completed | 94% AR statement download failed, Cashiering Fail due to non-availablity of Credit Cards, Bank Check details missmatch for Subaru of Lethbridge - 6900
Daniels Chevrolet Buick GMC- 6804 | 2025-09-23 | USA East | XS | Conquest | 2025-09-16 | 38 | Completed | Completed | Lokesh | Completed | 100% for Daniels Chevrolet Buick GMC - 6804
Walt Massey Kia of McComb- 6997 | 2025-09-22 | USA East | XS | Buy/Sell | 2025-09-15 | 38 | Completed | Pending | Amaresh | Need to Check
MAG CDJR- 6982 | 2025-09-26 | USA East | XS | Buy/Sell | 2025-09-19 | 38 | Completed | Not yet started | Sujatha | Need to Check | NA
Brady Chrysler Dodge Jeep Ram- 6890 | 2025-09-30 | USA West and Central | S | Conquest | 2025-09-23 | 39 | Completed | Completed | Nanjunda | Completed | Pass
LeMars Chevrolet GMC- 7044 | 2025-09-30 | USA East | S | Buy/Sell | 2025-09-23 | 39 | Completed | Pending | Divya | Need to Check | NA
DCD 1-HQ- 7063 | 2025-09-30 | USA East | XS | Conquest | 2025-09-23 | 39 | Pending | Pending | NA | Unable To Complete | NA, Management Store
DCD MA Parts Warehouse- 6882 | 2025-09-30 | Mid Market | XS | Conquest | 2025-09-23 | 39 | Pending | Pending | NA | Unable To Complete | NA, Management Store
Diehl Chevrolet of North Hills- 7018 | 2025-09-30 | USA East | XS | Buy/Sell | 2025-09-23 | 39 | Completed | Pending | Sujatha | Completed | NA
Gunther Daytona- 6879 | 2025-09-30 | USA East | S | Conquest | 2025-09-23 | 39 | Completed | Completed | Divya | Completed | Pass
Neptune Motors LLC- 7055 | 2025-09-30 | USA East | XS | Buy/Sell | 2025-09-23 | 39 | Completed | Pending | Sujatha | Completed | Sales orders and OEM purchase orders have failed due to parts not being loaded. A basic repair order was created without parts. Additionally, vehicle inventory has not been loaded; therefore, we have built a sample vehicle to proceed with deals testing.
Nucar Chevrolet of Norwood- 5946 | 2025-09-30 | Mid Market | S | Conquest | 2025-09-23 | 39 | Completed | Completed | Divya | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar Honda West- 5949 | 2025-09-30 | Mid Market | XS | Conquest | 2025-09-23 | 39 | Completed | Completed | Sujatha | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar Honda of Norwood- 5940 | 2025-09-30 | Mid Market | XS | Conquest | 2025-09-23 | 39 | Completed | Completed | Nanjunda | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar Hyundai of Norwood- 5937 | 2025-09-30 | Mid Market | S | Conquest | 2025-09-23 | 39 | Completed | Completed | Divya | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar Lannan Chevrolet of Lowell- 5948 | 2025-09-30 | Mid Market | S | Conquest | 2025-09-23 | 39 | Completed | Completed | Sujatha | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar Lannan Chevrolet of Woburn- 5950 | 2025-09-30 | Mid Market | XS | Conquest | 2025-09-23 | 39 | Completed | Completed | Nanjunda | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar NISSAN SOUTH- 5938 | 2025-09-30 | Mid Market | S | Conquest | 2025-09-23 | 39 | Completed | Completed | Divya | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar Nissan of Norwood- 5936 | 2025-09-30 | Mid Market | XS | Conquest | 2025-09-23 | 39 | Completed | Completed | Lokesh | Completed
Nucar Toyota South- 5945 | 2025-09-30 | Mid Market | S | Conquest | 2025-09-23 | 39 | Completed | Completed | Nanjunda | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar Toyota of Norwood- 5944 | 2025-09-30 | Mid Market | S | Conquest | 2025-09-23 | 39 | Completed | Completed | Divya | Completed | Fail Dealer code not update as the configuration is not completed by config team
Nucar Volkswagen of Norwood- 5942 | 2025-09-30 | Mid Market | XS | Conquest | 2025-09-23 | 39 | Completed | Completed | Sujatha | Completed | Pass
Cadillac Arlington- 6915 | 2025-10-06 | USA East | S | Buy/Sell | 2025-09-29 | 40 | Completed | Pending | Divya | Need to Check
Cadillac Fort Worth- 6917 | 2025-10-06 | USA East | S | Buy/Sell | 2025-09-29 | 40 | Completed | Pending | Nanjunda | Need To Check
Casa Chevrolet Cadillac of Prescott- 6926 | 2025-10-07 | Mid Market | S | Conquest | 2025-09-30 | 40 | Completed | Completed | Sujatha | Completed | AR statement download failed
Casa Nissan of Prescott- 6927 | 2025-10-07 | Mid Market | XS | Conquest | 2025-09-30 | 40 | Completed | Completed | Divya | Completed
Eby Ford Lincoln- 6916 | 2025-10-07 | USA East | S | Conquest | 2025-09-30 | 40 | Completed | Completed | Nanjunda | Completed | AR statement download failed
Elco Chevrolet Cadillac- 6911 | 2025-10-07 | USA West and Central | XL | Conquest | 2025-09-30 | 40 | Completed | Completed | Sujatha | Completed | AR statement download failed
Stokes Hodges Kia- 6912 | 2025-10-07 | Mid Market | S | Conquest | 2025-09-30 | 40 | Pending | Pending | Divya | Completed | ISSUE WITH PARTS FULLFILMENT / https://tap.tekioncloud.com/support/tickets?ticketId=1513923
Sanborn Chevrolet- 6908 | 2025-10-07 | USA West and Central | S | Conquest | 2025-09-30 | 40 | Completed | Completed | Nanjunda | Completed | AR statement download failed
Stokes Hodges Ford- 6913 | 2025-10-07 | Mid Market | S | Conquest | 2025-09-30 | 40 | Completed | Completed | Sujatha | Completed | AR statement download failed
Honda Cars of Aiken- 6914 | 2025-10-07 | Mid Market | S | Conquest | 2025-09-30 | 40 | Completed | Completed | Divya | Completed
The Luxury Collection Walnut Creek- 6943 | 2025-10-07 | Mid Market | XS | Conquest | 2025-09-30 | 40 | Completed | Completed | Nanjunda | Completed | AR statement download failed and unable to create purchase order OEM
Custom Truck Accessories - Carson City, NV- 6931 | 2025-10-01 | USA East | S | New Point | 2025-09-24 | 39 |  |  | Sujatha
Custom Truck Accessories - Reno, NV- 6925 | 2025-10-01 | USA East | XS | New Point | 2025-09-24 | 39 |  |  | Sujatha
Ken Garff Honda of Orem- 6896 | 2025-10-12 | Enterprise | M | Conquest | 2025-10-05 | 41 |  |  | Nanjunda | Completed | Opcodes are not loading, AR statement download failed
Ken Garff Nissan of Orem- 6894 | 2025-10-12 | Enterprise | S | Conquest | 2025-10-05 | 41 | Completed |  | Nanjunda | Completed | Opcodes are not loading, AR statement download failed and unable to create purchase order OEM
Ken Garff Volkswagen- 6895 | 2025-10-12 | Enterprise | XS | Conquest | 2025-10-05 | 41 | Completed |  | Lokesh | WIP
Butler Chevrolet- 6933 | 2025-10-12 | Mid Market | S | Conquest | 2025-10-05 | 41 |  |  | Divya | Completed | Dealer code is missing in Purchase order
Speck Ford of Prosser | 2025-10-13 | USA West and Central | XS | Buy/Sell | 2025-10-06 | 41 |  |  | Amaresh
Butler Honda- 6886 | 2025-10-14 | Mid Market | XS | Conquest | 2025-10-07 | 41 |  |  | Divya | Completed | Dealer code is missing in Purchase order
Liberty CDJR- 7010 | 2025-10-14 | USA East | XS | New Point | 2025-10-07 | 41 |  |  | Nanjunda | Unable To Complete | GLAM Pending - EM
Passport Infiniti of Alexandria- 6790 | 2025-10-14 | Mid Market | S | Conquest | 2025-10-07 | 41 |  |  | Nanjunda | Completed | AR statement download failed
Passport Nissan of Alexandria- 6899 | 2025-10-14 | Mid Market | S | Conquest | 2025-10-07 | 41 |  |  | Nanjunda | Completed | AR statement download failed and There is no data in AR Aging report to create Cash receipts.
Passport of Alexandria Inc- 6828 | 2025-10-14 | Mid Market | S | Conquest | 2025-10-07 | 41 |  |  | Nanjunda | Completed | AR statement download failed and Unable to select the customer name from the dropdown in the AR Cash Receipt tile.
Irvine Acura- 5811 | 2025-10-14 | USA West and Central | S | Buy/Sell | 2025-10-07 | 41 |  |  | Nanjunda
Ineos Grenadier of Irvine- 7073 | 2025-10-14 | Mid Market | XS | Buy/Sell | 2025-10-07 | 41 |  |  | Nanjunda | Unable To Complete | GLAM Pending - EM and No parts are loaded
Pine Belt Chrysler Jeep- 6942 | 2025-10-21 | Usa East |  | Conquest | 2025-10-14 | 42 |  |  | Lokesh | WIP
Pine Belt Chevrolet- 6994 | 2025-10-21 | Usa East |  | Conquest | 2025-10-14 | 42 |  |  | Lokesh | WIP
Pine Belt Mazda- 6938 | 2025-10-21 | Usa East |  | Conquest | 2025-10-14 | 42 |  |  | Amaresh
Pine Belt Subaru- 6937 | 2025-10-21 | Usa East |  | Conquest | 2025-10-14 | 42 |  |  | Amaresh
Formulas:
SIM Start Date = [Go-Live Date]-7
Week Count = WEEKNUM([SIM Start Date])

## Sheet5
Rate after maximum hours (optional)
Start Entering Matrix from Row 5
Hours in Column A must be Integer Values
Hours | 0 | 0.1 | 0.2 | 0.3 | 0.4 | 0.5 | 0.6 | 0.7 | 0.8 | 0.9
0 | 0 | 25.95 | 52.95 | 78.95 | 111.88 | 131.95 | 155.95 | 181.95 | 207.95 | 233.95
1 | 265 | 306.88 | 333.95 | 361.95 | 389.95 | 397.88 | 428.88 | 519.88 | 560.88 | 589.88
2 | 630.95 | 668.88 | 701.88 | 734.88 | 767.95 | 800.95 | 827.88 | 860.95 | 894.88 | 927.95
3 | 961.88 | 994.88 | 1026.88 | 1058.88 | 1090.88 | 1122.88 | 1154.88 | 1186.88 | 1218.88 | 1250.95 | 25.95 | 52.95 | 78.95 | 111.88 | 131.95 | 155.95 | 181.95 | 207.95 | 233.95 | 265
4 | 1282.95 | 1314.95 | 1346.95 | 1378.95 | 1410.95 | 1442.95 | 1474.95 | 1507.88 | 1539.88 | 1571.88 | 306.88 | 333.95 | 361.95 | 389.95 | 397.88 | 428.88 | 519.88 | 560.88 | 589.88 | 630.95
5 | 1603.88 | 1635.88 | 1667.88 | 1699.88 | 1731.95 | 1763.95 | 1795.95 | 1827.95 | 1859.95 | 1891.95 | 668.88 | 701.88 | 734.88 | 767.95 | 800.95 | 827.88 | 860.95 | 894.88 | 927.95 | 961.88
6 | 1923.95 | 1955.95 | 1988.88 | 2020.88 | 2052.88 | 2084.88 | 2116.88 | 2148.88 | 2180.88 | 2212.88 | 994.88 | 1026.88 | 1058.88 | 1090.88 | 1122.88 | 1154.88 | 1186.88 | 1218.88 | 1250.95 | 1282.95
7 | 2244.95 | 2276.95 | 2308.95 | 2340.95 | 2372.95 | 2404.95 | 2436.95 | 2469.88 | 2501.88 | 2533.88 | 1314.95 | 1346.95 | 1378.95 | 1410.95 | 1442.95 | 1474.95 | 1507.88 | 1539.88 | 1571.88 | 1603.88
8 | 2565.88 | 2597.88 | 2629.88 | 2661.88 | 2693.88 | 2725.95 | 2757.95 | 2789.95 | 2821.95 | 2853.95 | 1635.88 | 1667.88 | 1699.88 | 1731.95 | 1763.95 | 1795.95 | 1827.95 | 1859.95 | 1891.95 | 1923.95
9 | 2885.95 | 2942.88 | 2974.88 | 3006.95 | 3039.88 | 3071.88 | 3103.95 | 3136.88 | 3168.88 | 3200.95 | 1955.95 | 1988.88 | 2020.88 | 2052.88 | 2084.88 | 2116.88 | 2148.88 | 2180.88 | 2212.88 | 2244.95
10 | 3233.88 | 3265.88 | 3297.95 | 3329.95 | 3362.88 | 3394.95 | 3426.95 | 3459.88 | 3491.95 | 3523.95 | 2276.95 | 2308.95 | 2340.95 | 2372.95 | 2404.95 | 2436.95 | 2469.88 | 2501.88 | 2533.88 | 2565.88
11 | 3556.88 | 3588.95 | 3620.95 | 3653.88 | 3685.95 | 3717.95 | 3750.88 | 3782.95 | 3814.95 | 3847.88 | 2597.88 | 2629.88 | 2661.88 | 2693.88 | 2725.95 | 2757.95 | 2789.95 | 2821.95 | 2853.95 | 2885.95
12 | 3879.95 | 3944.88 | 3976.95 | 4009.88 | 4041.95 | 4074.88 | 4106.95 | 4139.95 | 4172.88 | 4204.95 | 2942.88 | 2974.88 | 3006.95 | 3039.88 | 3071.88 | 3103.95 | 3136.88 | 3168.88 | 3200.95 | 3233.88
13 | 4237.88 | 4269.95 | 4302.95 | 4335.88 | 4367.95 | 4400.88 | 4432.95 | 4465.95 | 4498.88 | 4530.95 | 3265.88 | 3297.95 | 3329.95 | 3362.88 | 3394.95 | 3426.95 | 3459.88 | 3491.95 | 3523.95 | 3556.88
14 | 4563.88 | 4595.95 | 4628.88 | 4661.88 | 4693.95 | 4726.88 | 4758.95 | 4791.88 | 4824.88 | 4856.95 | 3588.95 | 3620.95 | 3653.88 | 3685.95 | 3717.95 | 3750.88 | 3782.95 | 3814.95 | 3847.88 | 3879.95
15 | 4889.88 | 4961.95 | 4994.95 | 5027.95 | 5060.88 | 5093.88 | 5126.88 | 5159.88 | 5191.95 | 5224.95 | 3944.88 | 3976.95 | 4009.88 | 4041.95 | 4074.88 | 4106.95 | 4139.95 | 4172.88 | 4204.95 | 4237.88
16 | 5257.95 | 5290.88 | 5323.88 | 5356.88 | 5389.88 | 5421.95 | 5454.95 | 5487.95 | 5520.88 | 5553.88 | 4269.95 | 4302.95 | 4335.88 | 4367.95 | 4400.88 | 4432.95 | 4465.95 | 4498.88 | 4530.95 | 4563.88
17 | 5586.88 | 5619.88 | 5651.95 | 5684.95 | 5717.95 | 5750.88 | 5783.88 | 5816.88 | 5849.88 | 5881.95 | 4595.95 | 4628.88 | 4661.88 | 4693.95 | 4726.88 | 4758.95 | 4791.88 | 4824.88 | 4856.95 | 4889.88
18 | 0: 5914.95 | 4961.95 | 4994.95 | 5027.95 | 5060.88 | 5093.88 | 5126.88 | 5159.88 | 5191.95 | 5224.95 | 5257.95
19 | [10 empty] | 5290.88 | 5323.88 | 5356.88 | 5389.88 | 5421.95 | 5454.95 | 5487.95 | 5520.88 | 5553.88 | 5586.88
[11 empty] | 5619.88 | 5651.95 | 5684.95 | 5717.95 | 5750.88 | 5783.88 | 5816.88 | 5849.88 | 5881.95 | 5914.95

## Sheet3
Store Name/ID | Go - Live date | Assigned | Status
Young Ford of Brigham City - 6840 | 2025-08-26 | Sujatha
Honda Milton Martin Honda- 6773 | 2025-08-19 | Divya
Nanjunda
Divya
[5 empty] | Go-Live Date | Assignee | Testing Status

## Sheet4
Burt Watson GMC, LLC - 6832
Clay Cooley Hyundai of Sherman - 7006
South Richmond Chrysler Dodge Jeep Ram - 6858
Gunther Clermont - 6747
Oakes Kia 2 - 6824
Mike Fair GM Perth - 6874
Stokes Volkswagon - 6801
Stokes Kia - 6800
Stokes Chevrolet of Moncks Corner - 6799
Stokes Honda North - 6803
Stokes Mazda - 6802
Courtesy Subaru - 6862
Chuck Anderson Ford - 6831
Daniels Chevrolet Buick GMC - 6804
Passport Infiniti of Alexandria - 6790

## Sheet2
Dealership Name | Go-live
Marthaler Honda of Helena- 6835 | 2025-07-15
OpenRoad Audi Boundary- 6740 | 2025-07-15
OpenRoad Group- 6744 | 2025-07-15
OpenRoad Volkswagen Burnaby- 6735 | 2025-07-15
Phillips Auto Group of Bradley- 6733 | 2025-07-15
Phillips Chevrolet of Frankfort- 6731 | 2025-07-15
Phillips Chevrolet of Lansing- 6732 | 2025-07-15
STG Auto Group of Chandler- 6850 | 2025-07-15
STG Dealership Holdings LLC- 6902 | 2025-07-15
Koons Ford Falls Church- 6619 | 2025-07-21
Infiniti of Suitland- 6706 | 2025-07-22
Passport Mazda- 6710 | 2025-07-22
Passport BMW- 6705 | 2025-07-22
Larson Cadillac- 6724 | 2025-07-22
Larson Dodge- 6723 | 2025-07-22
Porsche Tacoma- 6725 | 2025-07-22
Larson Hyundai of Tacoma- 6726 | 2025-07-22
Mercedes-Benz of Tacoma- 6727 | 2025-07-22
Volkswagen of Tacoma- 6728 | 2025-07-22
Audi Tacoma- 6730 | 2025-07-22
Larson Auto Group Mgmt Co- 6888 | 2025-07-22
Marthaler Honda- 5801 | 2025-07-22
Passport Toyota- 6709 | 2025-07-22
Passport Nissan of Marlow Heights- 6708 | 2025-07-22
Mini of Montgomery County- 6707 | 2025-07-22
Stott's Ford Inc- 6715 | 2025-07-22
Toyota of Tacoma- 6729 | 2025-07-22
Wild Rose Chevrolet- 6711 | 2025-07-22
Chrysler Dodge Jeep RAM Bountiful- 6878 | 2025-07-27
Lexus of Murray- 6758 | 2025-07-27
Lexus of Lindon- 6751 | 2025-07-27
Connell Chevrolet- 6898 | 2025-07-28
Ferrari of Seattle- 6739 | 2025-07-29
Audi Rancho Mirage- 6608 | 2025-07-29
Jaguar Land Rover Rancho Mirage- 6609 | 2025-07-29
Desert European Motors- 5819 | 2025-07-29
Leskovar Honda- 6754 | 2025-07-29
Lethbridge Volkswagen- 6889 | 2025-07-29
Maserati-Alfa Romeo of Seattle | 2025-07-29
Stevens Ford- 6749 | 2025-07-29
Wilson Toyota- 6753 | 2025-07-29
Clay Cooley VW of Lewisville- 6903 | 2025-07-30
Three-Way Chevrolet-Cadillac- 6736 | 2025-07-30
Store Details | SIM Week | Type of Implemenation
Walser Auto Shield- 6830 | 2025-07-29 | New Point
Kennedy Automotive Consulting Inc- 6798 | 2025-07-29 | Conquest
Kennedy Automotive Group- 6787 | 2025-07-29 | Conquest
Stoler Chevrolet Buick- 6887 | 2025-07-29 | Buy and Sell
Audi South Atlanta- 6794 | 2025-07-29 | Conquest
Bulldog Kia- 6792 | 2025-07-29 | Conquest
John Kennedy Ford Mazda- 6780 | 2025-07-29 | Conquest
John Kennedy Ford- 6779 | 2025-07-29 | Conquest
John Kennedy Ford Jenkintown- 6781 | 2025-07-29 | Conquest
John Kennedy Ford Phoenixville- 6782 | 2025-07-29 | Conquest
John Kennedy Ford Lincoln Mazda Pottstown- 6777 | 2025-07-29 | Conquest
John Kennedy Subaru Inc- 6786 | 2025-07-29 | Conquest
Luv Toyota of Bradford- 6763 | 2025-07-29 | Conquest
John Kennedy Collision Center of Willow Grove- 6778 | 2025-07-29 | Conquest
Butler Lexus of South Atlanta- 6793 | 2025-07-29 | Conquest
Ferrari of Salt Lake City- 5809 | 2025-07-29 | Conquest
Store Details | SIM Week | Type of Implemenation | Comments
Young Used Center- 6836 | 2025-08-18 | Conquest | Configuration Pending - Handled by POD directrly
Mercedes Benz of Midlothian - 6924 | 2025-08-18 | Conquest | Parts not laoded
Merccdes-Benz of Richmond - 6922 | 2025-08-18 | Conquest | Parts not laoded
Daniels Chevrolet Buick GMC - 6804 | 2025-08-18 | Conquest | Parts not laoded
Folsom Lake CDJR - 6784 | 2025-08-18 | Conquest | Parts are locked, Need user code from Admin
Grubbs Acura of Tulsa - 2473 | 2025-08-18 | Conquest | Configuration Pending - Handled by POD directrly
Passport Infiniti of Alexandria - 6790 | 2025-08-18 | Conquest | Parts not laoded.
Young Chrysler Jeep Dodge Ram Morgan - 6839 | 2025-08-18 | Conquest | RO Posting Issue
Young Ford of Brigham City - 6840 | 2025-08-18 | Conquest | completed
Young Honda - 6837 | 2025-08-18 | Conquest | Creating RO issue
Store Details | SIM Week | Type of Implemenation | Comments
Young Used Center- 6836 | 2025-08-18 | Conquest | Configuration Pending - Handled by POD directrly
Mercedes Benz of Midlothian - 6924 | 2025-08-18 | Conquest | Parts not laoded
Merccdes-Benz of Richmond - 6922 | 2025-08-18 | Conquest | Parts not laoded
Daniels Chevrolet Buick GMC - 6804 | 2025-08-18 | Conquest | Parts not laoded
Folsom Lake CDJR - 6784 | 2025-08-18 | Conquest | Parts are locked, Need user code from Admin
Grubbs Acura of Tulsa - 2473 | 2025-08-18 | Conquest | Configuration Pending - Handled by POD directrly
Passport Infiniti of Alexandria - 6790 | 2025-08-18 | Conquest | Parts not laoded.
Young Chrysler Jeep Dodge Ram Morgan - 6839 | 2025-08-18 | Conquest | RO Posting Issue
Young Honda - 6837 | 2025-08-18 | Conquest | Creating RO issue

## Sheet6 (hidden)
DCD 1-HQ- 7063 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_7063 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_7063 | DONE
Nucar Honda of Norwood- 5940 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5940 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5940 | DONE
Nucar Toyota of Norwood- 5944 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5944 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5944 | DONE
Nucar Toyota South- 5945 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5945 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5945 | DONE
Nucar Chevrolet of Norwood- 5946 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5946 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5946 | DONE
Nucar Hyundai of Norwood- 5937 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5937 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5937 | DONE
Nucar Nissan of Norwood- 5936 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5936 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5936 | DONE
Nucar Lannan Chevrolet of Lowell- 5948 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5948 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5948 | DONE
Nucar Volkswagen of Norwood- 5942 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5942 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5942 | DONE
Nucar Lannan Chevrolet of Woburn- 5950 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5950 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5950
DCD MA Parts Warehouse- 6882 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_6882 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_6882
Nucar NISSAN SOUTH- 5938 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5938 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5938
Nucar Honda West- 5949 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5949 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5949
Nucar Automall of Tilton- 5939 | https://preprod-conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5939 | https://conscheduling.tekioncloud.com/consumer-scheduling/sign-in/phone?accessToken=dcdautomotive_435_5939