## August Go Live
Assignee | Go Live Date | Implementation Type | SIM Start Date | Dealership Name | Region | Parts - Status | Service - Status | Accounting - Status | CP LINK Created | Comments | Missing DOCS | Communication Templates | Go Live date changed
Karan Thakur | 2025-08-01 | New Point | 2025-07-25 | Walser Auto Shield-6830 | Mid Market | Completed | Completed | Completed | Yes |  | PDF & Parts Invoice> Asked from Bradley | Completed | No | 23
Karan Thakur | 2025-08-05 | Conquest | 2025-07-29 | Audi South Atlanta-6794 | Mid Market | Completed | Completed | Completed | Yes |  | MPVI, PDF docs, Labor grid, voided check, parts invoice (customer copy) | Completed | No
Tummuru Lokesh Reddy | 2025-08-05 | Conquest | 2025-07-29 | Bulldog Kia-6792 | Mid Market | Completed | Completed | Completed | Yes |  | Inspection doc | Completed | No
Amaresh M | 2025-08-06 | Conquest | 2025-07-30 | Butler Lexus of South Atlanta-6793 | Mid Market | Completed | Completed | Completed | Yes |  | Labor grid is missing, Voided check | Completed | No
Tummuru Lokesh Reddy | 2025-08-05 | Conquest | 2025-07-29 | John Kennedy Ford Mazda-6780 | Mid Market | Completed | Completed | Completed | Yes |  | Inspection doc & Service Invoice | Completed | No
Amaresh M | 2025-08-05 | Conquest | 2025-07-29 | John Kennedy Ford-6779 | Mid Market | Completed | Completed | Completed | Yes |  | MPVI, Service Invoice, Parts Invoice, Matrix, Labor Grid | Completed | No
Tummuru Lokesh Reddy | 2025-08-05 | Conquest | 2025-07-29 | John Kennedy Ford Jenkintown-6781 | Mid Market | Completed | Completed | Completed | Yes |  | Parts Invoice, Matrix and Service Invoice, Inspection doc | Completed | No
Karan Thakur | 2025-08-05 | Conquest | 2025-07-29 | John Kennedy Ford Phoenixville-6782 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed | No
Karan Thakur | 2025-08-05 | Conquest | 2025-07-29 | John Kennedy Ford Lincoln Mazda Pottstown-6777 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-05 | Conquest | 2025-07-29 | John Kennedy Subaru Inc-6786 | Mid Market | Completed | Completed | Completed | Yes |  | Inspection doc & Service Invoice | Completed | No
Karan Thakur | 2025-08-04 | Conquest | 2025-07-28 | Kennedy Automotive Consulting Inc-6798 | Mid Market | Not Configured | Not Configured | Not Configured | Not Configured | Handled by POD team |  | Completed | No
Amaresh M | 2025-08-04 | Conquest | 2025-07-28 | Kennedy Automotive Group-6787 | Mid Market | Not Configured | Not Configured | Not Configured | Not Configured | Handled by POD team |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-19 | Conquest | 2025-08-12 | ALM CDJR Perry -6881 | Mid Market | Completed | Completed | Completed | Yes |  | 5772 | Completed | No
Karan Thakur | 2025-08-19 | Conquest | 2025-08-12 | ALM Kia of Perry -6880 | Mid Market | Completed | Completed | Completed | Yes |  | 5772 | Completed | No
Karan Thakur | 2025-08-05 | Conquest | 2025-07-29 | John Kennedy Collision Center of Willow Grove-6778 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-10 | Conquest | 2025-08-03 | Ferrari of Salt Lake City-5809 | Enterprise | Not Configured | Not Configured | Not Configured | Not Configured | BP Issue |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-13 | Conquest | 2025-08-06 | Liberty Auto City Subaru-6768 | USA East | Completed | Completed | Completed | Yes |  |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-13 | Conquest | 2025-08-06 | Liberty Chrysler Dodge Jeep Ram-6769 | USA East | Completed | Completed | Completed | Yes |  |  | Completed | No
Karan Thakur | 2025-08-12 | Conquest | 2025-08-05 | Nucar Automall of St Albans-5947 | Mid Market | Not Configured | Not Configured | Not Configured | Not Configured | BP Issue |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-12 | Conquest | 2025-08-05 | Polestar Marin-6844 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed | No
Amaresh M | 2025-08-12 | Conquest | 2025-08-05 | Volvo Cars Marin-6845 | Mid Market | Completed | Completed | Completed | Yes |  | Pricing matrix | Completed | No
Karan Thakur | 2025-08-10 | Conquest | 2025-08-03 | Ken Garff Mercedes-6719 | Enterprise | Not Configured | Not Configured | Not Configured | Not Configured | ENTERPRISE |  |  | No
Amaresh M | 2025-08-10 | Conquest | 2025-08-03 | Ken Garff Volvo-6721 | Enterprise | Not Configured | Not Configured | Not Configured | Not Configured | ENTERPRISE |  |  | No
Karan Thakur | 2025-08-19 | Conquest | 2025-08-12 | Butler Lexus-6796 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-20 | Conquest | 2025-08-13 | Butler Nissan-6795 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed | No
Amaresh M | 2025-08-19 | Conquest | 2025-08-12 | Downtown Ford Sacramento-6847 | Mid Market | Completed | Completed | Completed | Yes |  | Pricing matrix | Completed | No
Tummuru Lokesh Reddy | 2025-08-20 | Conquest | 2025-08-13 | Honda Milton Martin Honda-6773 | USA East | Completed | Completed | Completed | Yes |  | MPVI | Completed | No
Amaresh M | 2025-11-04 | Conquest | 2025-10-28 | Butler Toyota-6797 | Mid Market | Completed | Completed | Completed | Yes |  |  |  | Yes, moved to November
Tummuru Lokesh Reddy | 2025-08-26 | Conquest | 2025-08-19 | Folsom Lake CDJR-6784 | USA West and Central | Completed | Completed | Completed | Yes |  | MPVI, Service Invoice | Completed | No
Tummuru Lokesh Reddy | 2025-08-26 | Conquest | 2025-08-19 | Young Automotive-6838 | Mid Market | Not Configured | Not Configured | Not Configured | Not Configured |  |  | Completed | No
Amaresh M | 2025-08-26 | Conquest | 2025-08-19 | Young Chrysler Jeep Dodge Ram Morgan-6839 | Mid Market | Not Configured | Not Configured | Not Configured | Not Configured | On Hold | Informed by Joey | Completed | No
Karan Thakur | 2025-08-26 | Conquest | 2025-08-19 | Young Ford of Brigham City-6840 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-26 | Conquest | 2025-08-19 | Young Honda-6837 | Mid Market | Completed | Completed | Completed | Yes |  | MPVI, Service Invoice |  | No
Karan Thakur | 2025-08-26 | Conquest | 2025-08-19 | Young Used Center-6836 | Mid Market | Not Configured | Not Configured | Not Configured | Not Configured |  |  |  | No
Amaresh M | 2025-08-19 | Conquest | 2025-08-12 | Jaguar Land Rover Marin-6848 | Mid Market | Completed | Completed | Completed | Yes |  | Pricing matrix | Completed | No
Karan Thakur | 2025-08-19 | Conquest | 2025-08-12 | MercedesBenz of Fairfield-6846 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed | No
Tummuru Lokesh Reddy | 2025-08-19 | Conquest | 2025-08-12 | Paul Sherry Chrysler-6829 | USA East | Completed | Completed | Completed | Yes |  |  | Done
Tummuru Lokesh Reddy | 2025-08-20 | Conquest | 2025-08-12 | Toyota Sunnyvale-6843 | Mid Market | Completed | Completed | Completed | Yes
Karan Thakur | 2025-08-04 | Buy/Sell | 2025-07-28 | Stoler Chevrolet Buick- 6887 | USA East | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell
Tummuru Lokesh Reddy | 2025-08-05 | Conquest | 2025-07-28 | Luv Toyota of Bradford- 6763 | USA East | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell
Amaresh M | 2025-08-14 | Buy/Sell | 2025-08-07 | Not Configuredpleton Palatine Hyundai- 6980 | USA East | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell
Amaresh M | 2025-08-14 | Buy/Sell | 2025-08-07 | Not Configuredpleton Palatine Chevy- 6979 | USA East | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell
Karan Thakur | 2025-08-18 | New Point | 2025-08-11 | Reydel Volkswagen of Freehold- 6897 | USA East | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell
Karan Thakur | 2025-08-18 | New Point | 2025-08-11 | ThinkFleet- 6995 | USA East | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell
Tummuru Lokesh Reddy | 2025-08-19 | New Point | 2025-08-12 | Maverick Motors DFW- 6928 | USA East | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell
Amaresh M | 2025-08-25 | New Point | 2025-08-18 | Mike Fair GM Perth- 6874 | Canada | Not Configured | Not Configured | Not Configured | Not Configured | New Point
Karan Thakur | 2025-08-26 | Conquest | 2025-08-18 | Grubbs Acura of Tulsa- 2473 | Mid Market | Completed | Completed | Completed | Yes
Amaresh M | 2025-08-26 | Buy/Sell | 2025-08-18 | Clay Cooley Hyundai of Sherman- 7006 | USA West and Central | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell
Karan Thakur | 2025-08-28 | Buy/Sell | 2025-08-20 | South Richmond Chrysler Dodge Jeep Ram- 6858 | USA East | Not Configured | Not Configured | Not Configured | Not Configured | Buy/Sell

## SEPT Go -Live
Assignee | Go Live Date | Implementation Type | SIM Start Date | Dealership Name | Region | Parts - Status | Service - Status | Accounting - Status | CP LINK Created | Comments | Missing DOCS | Communication Templates | Go Live date changed
Tummuru Lokesh Reddy | 2025-09-01 | New Point | 2025-08-25 | Gunther Clermont-6747 | USA East | Completed | Completed | Completed | Yes | Copy store |  | Completed
Tummuru Lokesh Reddy | 2025-09-01 | Buy/Sell | 2025-08-25 | Oakes Kia 2-6824 | USA East | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Karan Thakur | 2025-09-02 | Conquest | 2025-08-26 | Stokes Volkswagon-6801 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-02 | Conquest | 2025-08-26 | Stokes Kia-6800 | Mid Market | Completed | Completed | Completed | Yes |  | MPVI, Service invoice | Completed
Tummuru Lokesh Reddy | 2025-09-02 | Conquest | 2025-08-26 | Stokes Chevrolet of Moncks Corner-6799 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-02 | Conquest | 2025-08-26 | Stokes Honda North-6803 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed
Amaresh M | 2025-09-02 | Conquest | 2025-08-26 | Stokes Mazda-6802 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed
Amaresh M | 2025-09-03 | Conquest | 2025-08-27 | Courtesy Subaru-6862 | USA WEST | Completed | Completed | Completed | Yes | Accounting is configured by pod |  | Completed
Amaresh M | 2025-09-03 | Conquest | 2025-08-27 | Chuck Anderson Ford-6831 | USA West and Central | Completed | Completed | Completed | Yes |  | Voided check,P&S Invoice,matrix,MPVI | Completed
Not Configured | 2025-09-03 | Buy/Sell | 2025-08-27 | Burt Watson GMC, LLC-6832 | USA East | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Butler Chrysler Dodge Jeep-6885 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-09 | Conquest | 2025-09-02 | Jamestown Honda-6766 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Amaresh M | 2025-09-05 | Conquest | 2025-09-02 | Luv Toyota-6764 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-09 | Conquest | 2025-09-02 | Infiniti Stuart-6545 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Audi Stuart-6865 | USA East | Not Configured | Not Configured | Not Configured | Yes | Handled by POD team |  | Completed
Karan Thakur | 2025-09-09 | Conquest | 2025-09-02 | Bentley Jacksonville-6872 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Maserati Jacksonville-6869 | USA East | Not Configured | Not Configured | Not Configured | Yes | Handled by POD team |  | Completed
Tummuru Lokesh Reddy | 2025-09-09 | Conquest | 2025-09-02 | Maserati Stuart-6868 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Tummuru Lokesh Reddy | 2025-09-09 | Conquest | 2025-09-02 | Mohawk Chevrolet-6860 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Bentley Edison-6866 | USA East | Not Configured | Not Configured | Not Configured | Yes | Handled by POD team |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Porsche Centre Richmond-6825 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-09 | Conquest | 2025-09-02 | Scholfield Honda-6499 | USA West and Central | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Karan Thakur | 2025-09-09 | Conquest | 2025-09-02 | Maserati of Central New Jersey-6867 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Valdosta Toyota-6884 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed
Tummuru Lokesh Reddy | 2025-09-09 | Conquest | 2025-09-02 | Don Wood Chrysler Dodge Jeep-6901 | USA East | Completed | Completed | Completed | Yes | Copy store |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Don Wood Ford Lincoln-6909 | USA East | Completed | Completed | Completed | Yes | Copy store |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Don Wood Hyundai-6892 | USA East | Completed | Completed | Completed | Yes | Copy store |  | Completed
Karan Thakur | 2025-09-09 | Conquest | 2025-09-02 | Don Wood Toyota-6893 | USA East | Completed | Completed | Completed | Yes | Copy store |  | Completed
Amaresh M | 2025-09-09 | Conquest | 2025-09-02 | Don Wood Chevrolet-6891 | USA East | Completed | Completed | Completed | Yes | Copy store |  | Completed
Not Configured | 2025-09-14 | Conquest | 2025-09-07 | Ken Garff West Valley Chrysler Dodge Jeep Ram-6859 | Enterprise | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Karan Thakur | 2025-09-30 | Buy/Sell | 2025-09-22 | Diehl Chevrolet of North Hills-Not provisioned | USA East | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Karan Thakur | 2025-09-16 | Conquest | 2025-09-09 | Bob Grimm Chevrolet, Inc.-6870 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-16 | Conquest | 2025-09-09 | Dave Kring Chevrolet Inc-6877 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Amaresh M | 2025-09-16 | Conquest | 2025-09-09 | Carvilla-6905 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-16 | Conquest | 2025-09-09 | Honda of Westborough-6932 | Mid Market | Completed | Completed | Completed | Yes |  |  | Completed
Tummuru Lokesh Reddy | 2025-09-16 | Conquest | 2025-09-09 | LUV Kia of Jamestown-6765 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-16 | Conquest | 2025-09-09 | Porsche Centre Langley-6762 | Canda | Completed | Completed | Completed | Yes |  |  | Completed
Amaresh M | 2025-09-16 | Conquest | 2025-09-09 | Autoplex Atlanta-6904 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Amaresh M | 2025-09-16 | Conquest | 2025-09-09 | Watford Ford Lincoln-6827 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Not Configured | 2025-09-21 | Conquest | 2025-09-14 | Ken Garff Hyundai Downtown-6883 | Enterprise | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Not Configured | 2025-09-21 | Conquest | 2025-09-14 | Ken Garff Hyundai Southtowne-6907 | Enterprise | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Karan Thakur | 2025-09-23 | Conquest | 2025-09-16 | Gunther DaytoNot Configured-6879 | USA East | Completed | Completed | Completed | Yes | Handled by POD team |  | Completed
Amaresh M | 2025-09-23 | Conquest | 2025-09-16 | Honda of Downtown Chicago-6946 | USA East | Not Configured | Not Configured | Not Configured | Yes | Handled by POD team |  | Completed
Tummuru Lokesh Reddy | 2025-09-23 | Conquest | 2025-09-16 | Volkswagen Downtown Chicago-6947 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Karan Thakur | 2025-09-23 | Conquest | 2025-09-16 | Acura Highland Park -2408 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Amaresh M | 2025-09-23 | Conquest | 2025-09-16 | Honda Libertyville-6923 | USA East | Not Configured | Not Configured | Not Configured | Yes | Handled by POD team |  | Completed
Karan Thakur | 2025-09-23 | Conquest | 2025-09-16 | Subaru of Lethbridge-6900 | Canda | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Karan Thakur | 2025-09-23 | Conquest | 2025-09-16 | Daniels Chevrolet Buick GMC-6804 | USA East | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-30 | Conquest | 2025-09-23 | Brady Chrysler Dodge Jeep Ram-6890 | USA West and Central | Completed | Completed | Completed | Yes |  |  | Completed
Karan Thakur | 2025-09-30 | Conquest | 2025-09-23 | DCD MA Parts Warehouse-6882 | Mid Market | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar Chevrolet of Norwood-5946 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar Honda West-5949 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar Honda of Norwood-5940 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar Hyundai of Norwood-5937 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar LanNot Configuredn Chevrolet of Lowell-5948 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar LanNot Configuredn Chevrolet of Woburn-5950 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar NISSAN SOUTH-5938 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar Nissan of Norwood-5936 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar Toyota South-5945 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  | Completed
Tummuru Lokesh Reddy | 2025-09-30 | Conquest | 2025-09-23 | Westlock Motors Limited 2-6989 | Canda | Not Configured | Not Configured | Not Configured |  | Copy store |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar Volkswagen of Norwood-5942 | Mid Market | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-23 | Nucar Toyota of Norwood-5944 | Mid Market | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Amaresh M | 2025-09-23 | New Point | 2025-09-15 | Walser Kia-7062 | Mid Market | Completed | Completed | Completed | Yes | Copy store |  | Completed
Not Configured | 2025-09-11 | New Point | 2025-09-04 | Lifted Trucks Not Configuredshville – 7056 | USA East | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Not Configured | 2025-09-30 | Buy/Sell | 2025-09-22 | LeMars Chevrolet GMC – 7044 | USA East | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Not Configured | 2025-09-30 | Conquest | 2025-09-22 | DCD 1-HQ – 7063 | USA East | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Not Configured | 2025-09-30 | Buy/Sell | 2025-09-22 | Neptune Motors LLC – 7055 | USA East | Not Configured | Not Configured | Not Configured |  |  |  | Completed
Not Configured | 2025-09-02 | Buy/Sell | 2025-09-01 | Toyota Carlsbad – 7037 | USA East | Not Configured | Not Configured | Not Configured |  |  |  | Completed

## OCT Go Live
Assignee | Go Live Date | Implementation Type | SIM Start Date | Dealership Name | Region | Parts - Status | Service - Status | Accounting - Status | CP LINK Created | Comments | Missing DOCS | Communication Templates | Go Live date changed | TAP Tasks
Karan Thakur | 2025-10-01 | Buy/Sell | 2025-09-24 | Cadillac Arlington- 6915 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/123202/list?projectId=true
Amaresh M | 2025-10-01 | Buy/Sell | 2025-09-24 | Cadillac Fort Worth- 6917 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/123239/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-01 | Conquest | 2025-09-30 | Casa Chevrolet Cadillac of Prescott- 6926 | Mid Market | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/126067/list?projectId=true
Karan Thakur | 2025-10-07 | Conquest | 2025-09-30 | Casa Nissan of Prescott- 6927 | Mid Market | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/126081/list?projectId=true
Karan Thakur | 2025-10-07 | Conquest | 2025-09-30 | Eby Ford Lincoln- 6916 | USA East | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/117240/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-07 | Conquest | 2025-09-30 | Elco Chevrolet Cadillac- 6911 | USA West and Central | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/119353/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-07 | Conquest | 2025-09-30 | Stokes Hodges Kia- 6912 | Mid Market | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/119188/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-07 | Conquest | 2025-09-30 | Sanborn Chevrolet- 6908 | USA West and Central | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/109318/list?projectId=true
Karan Thakur | 2025-10-07 | Conquest | 2025-09-30 | Stokes Hodges Ford- 6913 | Mid Market | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/119197/list?projectId=true
Karan Thakur | 2025-10-07 | Conquest | 2025-09-30 | Honda Cars of Aiken- 6914 | Mid Market | Completed | Completed | Completed | [5 empty] | https://tap.tekioncloud.com/tm/projects/119218/list?projectId=true
Amaresh M | 2025-10-07 | Conquest | 2025-09-30 | The Luxury Collection Walnut Creek- 6943 | Mid Market | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/101861/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-07 | Conquest | 2025-10-05 | Ken Garff Honda of Orem- 6896 | Enterprise | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/118671/list?projectId=true
Karan Thakur | 2025-10-12 | Conquest | 2025-10-05 | Ken Garff Nissan of Orem- 6894 | Enterprise | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/118766/list?projectId=true
Amaresh M | 2025-10-12 | Conquest | 2025-10-05 | Ken Garff Volkswagen- 6895 | Enterprise | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/118788/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-12 | Conquest | 2025-10-07 | Butler Chevrolet- 6933 | Mid Market | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/118602/list?projectId=true
Karan Thakur | 2025-10-13 | New Point | 2025-10-07 | Custom Truck Accessories - Carson City, NV- 6931 | USA East | Not Configured | Not Configured | Not Configured | Yes | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/125027/list?projectId=true
Amaresh M | 2025-10-14 | New Point | 2025-10-07 | Custom Truck Accessories - Reno, NV- 6925 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/125013/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-14 | Buy/Sell | 2025-10-07 | Sewell KIA Buy/Sell- 6770 | USA East | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/122787/list?projectId=true
Amaresh M | 2025-10-14 | Conquest | 2025-10-14 | Bell and Bell Buick GMC - 6988 | Mid Market | Completed | Completed | Completed | Yes | COA not loaded |  |  |  | https://tap.tekioncloud.com/tm/projects/120654/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-14 | Conquest | 2025-10-14 | Gunther Coconut Creek- 6940 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/113559/list?projectId=true
Karan Thakur | 2025-10-14 | Conquest | 2025-10-14 | Gunther Delray Beach- 6939 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/113549/list?projectId=true
Amaresh M | 2025-10-14 | Conquest | 2025-10-14 | Pine Belt Chrysler Jeep- 6942 | USA East | Completed | Completed | Completed | Yes | Check in setup issue - https://tap.tekioncloud.com/support/tickets?ticketId=1479458 | Void check missing |  |  | https://tap.tekioncloud.com/tm/projects/119330/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-14 | Conquest | 2025-10-14 | Pine Belt Chevrolet- 6994 | USA East | Completed | Completed | Completed | Yes |  | Void check missing |  |  | https://tap.tekioncloud.com/tm/projects/119283/list?projectId=true
Karan Thakur | 2025-10-14 | Conquest | 2025-10-14 | Pine Belt Mazda- 6938 | USA East | Completed | Completed | Completed | Yes |  | Void check missing |  |  | https://tap.tekioncloud.com/tm/projects/119665/list?projectId=true
Amaresh M | 2025-10-14 | Conquest | 2025-10-14 | Pine Belt Subaru- 6937 | USA East | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/119305/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-14 | Conquest | 2025-10-19 | Ken Garff Porsche Lehi- 6720 | Enterprise | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/118831/list?projectId=true
Karan Thakur | 2025-10-14 | Conquest | 2025-10-19 | Ken Garff Audi Lehi- 6722 | Enterprise | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/118905/list?projectId=true
Amaresh M | 2025-10-21 | Conquest | 2025-10-20 | Hartwell Hereford- 6562 | United Kingdom | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/115486/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-21 | Conquest | 2025-10-21 | Alpha One Ford - 6996 | USA West and Central | Completed | Completed | WIP | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/119686/list?projectId=true
Karan Thakur | 2025-10-21 | Conquest | 2025-10-21 | Fallon Ford-Toyota- 6746 | USA West and Central | Completed | Completed | WIP |  | COA NOT LOADED |  |  |  | https://tap.tekioncloud.com/tm/projects/121175/list?projectId=true
Karan Thakur | 2025-10-21 | New Point | 2025-10-21 | Monument Motor Co LLC - 7040 | Mid Market | Not Configured | Not Configured | Not Configured |  | Handled by POD team |  |  |  | https://tap.tekioncloud.com/tm/projects/121942/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-21 | Conquest | 2025-10-21 | Mountain Home Chevrolet GMC | Mid Market | Not Configured | Not Configured | Not Configured |  | Not provisioned |  |  |  | https://tap.tekioncloud.com/tm/projects/122266/list?projectId=true
Karan Thakur | 2025-10-21 | Conquest | 2025-10-21 | Ontario Auto Ranch | Mid Market | Not Configured | Not Configured | Not Configured |  | Not Provisioned |  |  |  | https://tap.tekioncloud.com/tm/projects/122277/list?projectId=true
Amaresh M | 2025-10-21 | Conquest | 2025-10-21 | Ontario Auto Ranch Ford | Mid Market | Not Configured | Not Configured | Not Configured |  | Not Provisioned |  |  |  | https://tap.tekioncloud.com/tm/projects/122288/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-21 | Conquest | 2025-10-21 | Skalnek Ford- 6973 | USA East | Completed | Completed | Completed | Yes | COA NOT LOADED |  |  |  | https://tap.tekioncloud.com/tm/projects/121620/list?projectId=true
Karan Thakur | 2025-10-26 | Conquest | 2025-10-21 | Los Gatos Luxury Cars- 6961 | Mid Market | Completed | Completed | WIP |  | COA NOT LOADED |  |  |  | https://tap.tekioncloud.com/tm/projects/101744/list?projectId=true
Amaresh M | 2025-10-26 | Conquest | 2025-10-21 | Volvo Cars Palo Alto- 6962 | Mid Market | Completed | Completed | Completed | Yes |  |  |  |  | https://tap.tekioncloud.com/tm/projects/101848/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-27 | Conquest | 2025-10-21 | Auto Ranch Auto Group Mgmt Co - 6981 | USA West and Central | Not Configured | Not Configured | Not Configured | Yes | MaNot Configuredgement store |  |  |  | https://tap.tekioncloud.com/tm/projects/128036/list?projectId=true
Karan Thakur | 2025-10-28 | Conquest | 2025-10-21 | Baker City Auto Ranch- 6974 | Mid Market | Completed | Completed | WIP |  | COA not loaded |  |  |  | https://tap.tekioncloud.com/tm/projects/122292/list?projectId=true
Amaresh M | 2025-10-28 | Conquest | 2025-10-21 | Folsom Buick GMC- 6978 | USA West and Central | Completed | Completed | WIP |  | JourNot Configuredls not laoded |  |  |  | https://tap.tekioncloud.com/tm/projects/125085/list?projectId=true
Tummuru Lokesh Reddy | 2025-10-28 | Conquest | 2025-10-21 | Epic Chevrolet Cadillac - 6977 | USA West and Central | Completed | Completed | WIP |  | GLAM is Done/JourNot Configuredls not loaded yet |  |  |  | https://tap.tekioncloud.com/tm/projects/125104/list?projectId=true
Karan Thakur | 2025-10-28 | Conquest | 2025-10-21 | McLaren San Francisco- 6960 | Mid Market | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/128291/list?projectId=true
Amaresh M | 2025-10-28 | Conquest | 2025-10-21 | Mountain Home Auto Ranch- 6976 | Mid Market | Completed | Completed | WIP |  | COA not loaded |  |  |  | https://tap.tekioncloud.com/tm/projects/122320/list?projectId=true
Karan Thakur | 2025-10-28 | Conquest | 2025-10-21 | Stateline Auto Ranch Subaru- 6975 | Mid Market | WIP | WIP | WIP |  | COA not loaded |  |  |  | https://tap.tekioncloud.com/tm/projects/122344/list?projectId=true
Amaresh M | 2025-10-28 | Conquest | 2025-10-07 | Butler Honda- 6886 | Mid Market | Completed | Completed | Completed | Yes
Not Configured | 2025-10-28 | New Point | 2025-10-07 | Liberty CDJR- 7010 | USA East | Not Configured | Not Configured | Not Configured
Not Configured | 2025-10-28 | Buy/Sell | 2025-10-06 | Walt Massey Kia of McComb-6997 | USA East | Not Configured | Not Configured | Not Configured
Not Configured | 2025-10-28 | Buy/Sell | 2025-10-21 | MAG CDJR- 6982 | USA East | Not Configured | Not Configured | Not Configured
Amaresh M | 2025-10-28 | Conquest | 2025-10-07 | Passport Infiniti of Alexandria- 6790 | Mid Market | Completed | Completed | Completed
Tummuru Lokesh Reddy | 2025-10-28 | Conquest | 2025-10-07 | Passport Nissan of Alexandria- 6899 | Mid Market | Completed | Completed | Completed
Karan Thakur | 2025-10-28 | Conquest | 2025-10-07 | Passport of Alexandria Inc- 6828 | Mid Market | Completed | Completed | Completed
Not Configured | 2025-10-28 | Buy/Sell | 2025-10-07 | Irvine Acura- 5811 | USA West and Central | Not Configured | Not Configured | Not Configured
Not Configured | 2025-10-28 | Buy/Sell | 2025-10-07 | Ineos GreNot Configureddier of Irvine- 7073 | Mid Market | Not Configured | Not Configured | Not Configured
Not Configured | 2025-10-28 | Buy/Sell | 2025-10-14 | Young Chrysler Dodge Jeep of Riverdale- 7076 | Mid Market | Not Configured | Not Configured | Not Configured

## NOV Go Live
Assignee | Go Live Date | Implementation Type | SIM Start Date | Dealership Name | Region | Parts - Status | Service - Status | Accounting - Status | CP LINKS | Comments | Missing DOCS | Communication Templates | Go Live date changed | TASK Management
Karan Thakur | 2025-11-04 | Conquest | 2025-10-28 | Mercedes-Benz of Eugene- 6985 | USA West and Central | Completed | Completed | WIP |  | Journals not laoded |  |  |  | https://tap.tekioncloud.com/tm/projects/119456/portfolio?projectId=true
Tummuru Lokesh Reddy | 2025-11-04 | Conquest | 2025-10-28 | Wright Honda- 7060 | USA East | Completed | Completed | WIP | Yes | COA not loaded yet |  |  |  | https://tap.tekioncloud.com/tm/projects/128534/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-04 | Conquest | 2025-10-28 | Lundgren Ford- 6993 | USA West and Central | Completed | Completed | Completed | Yes | Accounting worked on by POD Team |  |  |  | https://tap.tekioncloud.com/tm/projects/119791/portfolio?projectId=true
Amaresh M | 2025-11-04 | Conquest | 2025-10-28 | Parkway Chrysler Dodge Ram Jeep- 6984 | USA West and Central | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/123759/portfolio?projectId=true
Amaresh M | 2025-11-04 | Conquest | 2025-10-28 | Parkway Chevrolet- 6986 | USA West and Central | Completed | Completed | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/123769/portfolio?projectId=true
Amaresh M | 2025-11-04 | Conquest | 2025-10-28 | Parkway Family Kia | USA West and Central | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/123716/portfolio?projectId=true
Amaresh M | 2025-11-04 | Conquest | 2025-10-28 | Parkway Family Mazda- 6987 | USA West and Central | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/123724/portfolio?projectId=true
Amaresh M | 2025-11-04 | Conquest | 2025-10-28 | Parkway Family Auto Group MaNot Configuredgement- 6983 | USA West and Central | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/123706/portfolio?projectId=true
Amaresh M | 2025-11-04 | Conquest | 2025-10-28 | Reagle Dodge- 6929 | USA East | Completed | Completed | WIP | Yes |  | Pricing matrix |  |  | https://tap.tekioncloud.com/tm/projects/124994/portfolio?projectId=true
Amaresh M | 2025-11-04 | Conquest | 2025-10-28 | Vista Ford Woodland Hills- 6857 | USA West and Central | Completed | Completed | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/121637/portfolio?projectId=true
Karan Thakur | 2025-11-04 | Conquest | 2025-10-28 | Wright Chevrolet Buick GMC- 7059 | USA East | Completed | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/128436/portfolio?projectId=true
Karan Thakur | 2025-11-04 | Conquest | 2025-10-28 | Genesis Of Wexford- 7066 | USA East | Completed | Completed | WIP | YES | COA not loaded |  |  |  | https://tap.tekioncloud.com/tm/projects/128556/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-04 | Conquest | 2025-10-28 | Wright Hyundai- 7064 | USA East | Completed | Completed | WIP |  | COA not loaded |  |  |  | https://tap.tekioncloud.com/tm/projects/128664/portfolio?projectId=true
Karan Thakur | 2025-11-10 | Conquest | 2025-11-03 | Not Configuredlley Hyundai | Enterprise | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/109789/portfolio?projectId=true
Not Configured | 2025-11-10 | Conquest | 2025-11-03 | Not Configuredlley Kia | Enterprise | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/109807/portfolio?projectId=true
Not Configured | 2025-11-10 | Conquest | 2025-11-03 | Not Configuredlley Toyota Stonecrest | Enterprise | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/109829/portfolio?projectId=true
Not Configured | 2025-11-10 | Conquest | 2025-11-03 | Not Configuredlley Toyota Union City | Enterprise | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/109860/portfolio?projectId=true
Not Configured | 2025-11-11 | Conquest | 2025-11-04 | Mercedes Benz of Midlothian- 6924 | Enterprise | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/102962/portfolio?projectId=true
Not Configured | 2025-11-11 | Conquest | 2025-11-04 | Mercddes-Benz of Richmond- 6922 | Enterprise | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/102984/portfolio?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | Anderson Automotive Group - Body Shop- 7005 | USA East | WIP | WIP | WIP |  | Config will be taken care by POD Team |  |  |  | https://tap.tekioncloud.com/tm/projects/130555/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | Anderson Automotive Group - MaNot Configuredgement Company- 7054 | USA East | Not Configured | Not Configured | WIP |  | No Accounting data in the BP, COA not Loaded. |  |  |  | https://tap.tekioncloud.com/tm/projects/132369/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | Anderson Honda- 6991 | USA East | Completed | WIP | WIP |  | Config will be taken care by POD Team |  |  |  | https://tap.tekioncloud.com/tm/projects/128818/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | Anderson Buick GMC of Abingdon- 6990 | USA East | Completed | WIP | WIP |  | Config will be taken care by POD Team |  |  |  | https://tap.tekioncloud.com/tm/projects/128765/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | Anderson Buick GMC of Hunt Valley- 6992 | USA East | Completed | WIP | WIP |  | Config will be taken care by POD Team |  |  |  | https://tap.tekioncloud.com/tm/projects/128870/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | CarVision Maple Shade | USA East | WIP | WIP | WIP |  | Moved to dec |  |  |  | https://tap.tekioncloud.com/tm/projects/132384/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | CarVision Trooper- 7077 | USA East | WIP | WIP | WIP |  | Moved to dec |  |  |  | https://tap.tekioncloud.com/tm/projects/132387/list?projectId=true
Amaresh M | 2025-11-11 | Conquest | 2025-11-04 | Gold Coast Acura- 2262 | USA West and Central | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/125065/portfolio?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | Grand Infiniti of Macon- 7032 | USA East | WIP | WIP | WIP |  | Complted |  |  |  | https://tap.tekioncloud.com/tm/projects/121816/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | Gunther Ft. Lauderdale- 6964 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/113577/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-11 | Conquest | 2025-11-04 | O'Brien Toyota- 7004 | USA East | WIP | WIP | WIP |  | Config will be taken care by POD Team |  |  |  | https://tap.tekioncloud.com/tm/projects/123835/list?projectId=true
Amaresh M | 2025-11-11 | Conquest | 2025-11-04 | Lexus of Westminster- 7043 | USA West and Central | Completed | Completed | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/128412/portfolio?projectId=true
Amaresh M | 2025-11-11 | Conquest | 2025-11-04 | Team Chevrolet- 6930 | USA West and Central | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/114897/portfolio?projectId=true
Karan Thakur | 2025-11-11 | Conquest | 2025-11-04 | Young Ford of Morgan- 7036 | Mid Market | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/120124/portfolio?projectId=true
Karan Thakur | 2025-11-11 | Conquest | 2025-11-04 | Young Kia- 7034 | Mid Market | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/120139/portfolio?projectId=true
Karan Thakur | 2025-11-11 | Conquest | 2025-11-04 | Young Subaru- 7035 | Mid Market | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/120197/portfolio?projectId=true
Karan Thakur | 2025-11-11 | Conquest | 2025-11-04 | Young Toyota- 7033 | Mid Market | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/120271/portfolio?projectId=true
Not Configured | 2025-11-11 | Conquest | 2025-11-04 | Not Configuredte Wade Subaru- 6668 | Enterprise | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/94453/portfolio?projectId=true
Tummuru Lokesh Reddy | 2025-11-16 | Conquest | 2025-11-09 | Automax Atlanta- 6972 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/126236/list?projectId=true
Karan Thakur | 2025-11-18 | Conquest | 2025-11-11 | Bob King Auto Group MaNot Configuredgement Company- 7025 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/121065/portfolio?projectId=true
Tummuru Lokesh Reddy | 2025-11-18 | Conquest | 2025-11-11 | Bob King Hyundai- 7021 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/121097/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-18 | New Point | 2025-11-11 | Genesis Automotive Corporate Office- 7027 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/126763/list?projectId=true
Karan Thakur | 2025-11-18 | Conquest | 2025-11-11 | Genesis Cadillac- 7026 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/126735/portfolio?projectId=true
Tummuru Lokesh Reddy | 2025-11-18 | Conquest | 2025-11-11 | Bob King Mazda- 7024 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/121127/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-18 | Conquest | 2025-11-11 | Genesis of Winston Salem- 7022 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/121073/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-18 | Conquest | 2025-11-11 | Bob King Kia- 7023 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/121143/list?projectId=true
Karan Thakur | 2025-11-18 | Conquest | 2025-11-11 | Polestar San Jose- 6963 | Mid Market | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/101805/portfolio?projectId=true
Tummuru Lokesh Reddy | 2025-11-18 | Conquest | 2025-11-11 | Sentry Ford Lincoln- 7019 | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/128079/list?projectId=true
Karan Thakur | 2025-11-18 | Conquest | 2025-11-11 |  | USA East | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/128068/portfolio?projectId=true
Karan Thakur | 2025-11-18 | Conquest | 2025-11-11 |  | Canada | WIP | WIP | WIP | [5 empty] | https://tap.tekioncloud.com/tm/projects/129652/portfolio?projectId=true
Tummuru Lokesh Reddy | 2025-11-18 | Conquest | 2025-11-11 | Anderson Buick GMC of Hunt Valley - 6992 | USA East | WIP | WIP | WIP |  |  |  | Copy store |  | https://tap.tekioncloud.com/tm/projects/128870/list?projectId=true
Tummuru Lokesh Reddy | 2025-11-18 | Conquest | 2025-11-11 | Westlock Motors Limited 2-6989 | Canada | Not Configured | Not Configured | Not Configured
AMARESH
KARAN
Lokesh
Completed
en
Formulas:
SIM Start Date = [Go Live Date]-7