## Aug 2025
Dealership Name | Implementation Type | Region | Configuration - Assigned | Go Live Date | Date of Completion | Configuration - User List | Configuration - BP | Configuration - Comments | Configuration - Status | Pre Go Live - Assigned to | Pre Go Live - Domain Updated | Pre Go Live - Set Up Check | Pre Go Live - Comments | Go Live Testing - Assigned To | Go Live Testing - Sample ADF | Go Live Testing - Inbound Email Test | Go Live Testing - Outbound Mail Test | Go Live Testing - Data Migration Test | Go Live Testing - Comments | Config team didn’t work on the store
Lewiston Auto Co., Inc. - 1067 | Conquest | USA West and Central | Not Configured | 2025-08-01 | NA | NA | NA | Config team didn’t work on the store | Not Configured | NA | NA | NA | Didn’t Perform Pre Go Live | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live | EM asked for standard Config
Akins Chevrolet - 6561 | Buy/Sell | USA East | Sujatha | 2025-08-04 | 2025-07-31 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues | CRM not enabled
Stoler Chevrolet Buick - 6887 | Buy/Sell | USA East | Nanjunda | 2025-08-04 | 2025-07-28 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues | Copy Store
Brown's Volkswagen - 6433 | Conquest | Canada | Nanjunda | 2025-08-05 | 2025-07-29 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
John Kennedy Ford Mazda - 6780 | Conquest | Mid Market | Nanjunda | 2025-08-05 | 2025-07-28 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
John Kennedy Ford - 6779 | Conquest | Mid Market | Sujatha | 2025-08-05 | 2025-07-09 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
John Kennedy Ford Jenkintown - 6781 | Conquest | Mid Market | Nanjunda | 2025-08-05 | 2025-07-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
John Kennedy Ford Phoenixville - 6782 | Conquest | Mid Market | Sujatha | 2025-08-05 | 2025-07-02 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
John Kennedy Ford Lincoln Mazda Pottstown - 6777 | Conquest | Mid Market | Nanjunda | 2025-08-05 | 2025-07-05 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
John Kennedy Subaru Inc - 6786 | Conquest | Mid Market | Nanjunda | 2025-08-05 | 2025-07-02 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
Luv Toyota of Bradford - 6763 | Conquest | USA East | Nanjunda | 2025-08-05 | 2025-06-24 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
Oremor of Glendale, LLC - 1851 | Conquest | USA West and Central | Sujatha | 2025-08-05 | 2025-07-29 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Ferrari of Salt Lake City - 5809 | Conquest | NA | Not Configured | 2025-08-10 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
Ken Garff Mercedes - 6719 | Conquest | NA | Not Configured | 2025-08-10 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
Ken Garff Volvo - 6721 | Conquest | NA | Not Configured | 2025-08-10 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
Blade Chevrolet, Inc - 1554 | Conquest | USA West and Central | Nanjunda | 2025-08-11 | 2025-05-30 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Wilson Toyota - 6753 | Conquest | USA West and Central | Nanjunda | 2025-08-11 | 2025-06-11 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | Migration Issues
Fairway Chevrolet GMC - 6527 | Conquest | USA East | Nanjunda | 2025-08-12 | 2025-06-23 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Fairway Ford - 6438 | Conquest | USA East | Nanjunda | 2025-08-12 | 2025-07-07 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Liberty Chrysler Dodge Jeep Ram - 6769 | Conquest | USA East | Nanjunda | 2025-08-12 | 2025-06-24 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
NA Motorcars, Inc. - 880 | Conquest | USA West and Central | Not Configured | 2025-08-14 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Napleton Palatine Hyundai - 6980 | Buy/Sell | USA East | Nanjunda | 2025-08-14 | 2025-08-11 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
Napleton Palatine Chevy - 6979 | Buy/Sell | USA East | Nanjunda | 2025-08-14 | 2025-08-11 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Didn’t Perform Go Live
Naguabo Auto Toyota - 6535 | Conquest | USA East | Nanjunda | 2025-08-18 | 2025-07-29 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Reydel Volkswagen of Freehold - 6897 | New Point | USA East | Sujatha | 2025-08-18 | 2025-07-18 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No | No | No | No | Domain not verified, EM confirmed this has been taken live but actual usage will begin next week, as it is a new point.
Milton Martin Honda - 6773 | Conquest | USA East | Nanjunda | 2025-08-19 | 2025-08-04 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Lethbridge Volkswagen - 6889 | Conquest | Canada | Nanjunda | 2025-08-19 | 2025-08-05 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Maverick Motors DFW - 6928 | New Point | USA West and Central | Not Configured | 2025-08-19 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
ALM CDJR Perry - 6881 | Conquest | Mid Market | Not Configured | 2025-08-19 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Paul Sherry Chrysler - 6829 | Conquest | USA East | Sujatha | 2025-08-19 | 2025-08-11 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
ALM Kia of Perry - 6880 | Conquest | Mid Market | Not Configured | 2025-08-19 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
Burt Watson GMC, LLC - 6832 | Buy/Sell | USA East | Nanjunda | 2025-08-25 | 2025-07-31 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
Bush Auto Group, Inc. - 1003 | Conquest | USA East | Sujatha | 2025-08-25 |  | No | No | CRM not enabled | NA | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Sewell Chevrolet GMC - 6568 | Conquest | USA West and Central | Nanjunda | 2025-08-25 | 2025-07-01 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
Grubbs Acura of Tulsa - 2473 | Conquest | Mid Market | Sujatha | 2025-08-26 | 2025-07-23 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | The communication templates caused an error in the process automation.
Gunther Clermont - 6747 | New Point | USA East | Sujatha | 2025-08-26 | 2025-06-20 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Sewell BMW of the Permian Basin - 6567 | Conquest | USA West and Central | Nanjunda | 2025-08-26 | 2025-07-01 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
Sewell Buick GMC Cadillac of Midland - 6570 | Conquest | USA West and Central | Nanjunda | 2025-08-26 | 2025-07-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
Sewell Chrysler Dodge Jeep Ram - 6571 | Conquest | USA West and Central | Nanjunda | 2025-08-26 | 2025-07-07 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
Sewell Ford Lincoln - 6566 | Conquest | USA West and Central | Nanjunda | 2025-08-26 | 2025-07-01 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
Young Honda - 6837 | Conquest | Mid Market | Nanjunda | 2025-08-26 | 2025-08-20 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Unable to Test | Golive date moved
Clay Cooley Hyundai of Sherman - 7006 | Buy/Sell | USA West and Central | Not Configured | 2025-08-27 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
South Richmond Chrysler Dodge Jeep Ram - 6858 | Buy/Sell | USA East | Nanjunda | 2025-08-29 | 2025-06-25 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues

## Sep 2025
Dealership Name | Implementation Type | Region | Configuration - Assigned | Go Live Date | Date of Completion | Configuration - User List | Configuration - BP | Configuration - Comments | Configuration - Status | Pre Go Live - Assigned to | Pre Go Live - Domain Updated | Pre Go Live - Set Up Check | Pre Go Live - Comments | Go Live Testing - Assigned To | Go Live Testing - Sample ADF | Go Live Testing - Inbound Email Test | Go Live Testing - Outbound Mail Test | Go Live Testing - Data Migration Test | Go Live Testing - Comments | Config team didn’t work on the store
Gunther Clermont - 6747 | New Point | USA East | Sujatha | 2025-09-01 | 2025-06-20 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No | No | No | No Issues | The domain was not verified at the time of go-live, which prevented us from receiving ADF. The issue was resolved the following day. | EM asked for standard Config
Luxury and Imports Leavenworth - 2546 | Conquest | USA West and Central | Not configured | 2025-09-01 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Nanjunda | No | No | No | No Issues | The domain was not updated during the go-live as it was pending from the dealer. It was updated later once received. | CRM not enabled
Cody Chevrolet Inc. - 1571 | Conquest | USA East | Not configured | 2025-09-02 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | The configuration team did not work, as the data was pending. The task was later completed by the EM | Copy Store
Ferrari of Seattle - 6739 | Conquest | USA West and Central | Not configured | 2025-09-02 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No | Template Issue was found Templates setups were not migrated- updated manully
Mike Fair GM Perth - 6874 | New Point | Canada | Sujatha | 2025-09-02 | 2025-07-18 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | The configuration team did not work, as the data was pending. The task was later completed by the EM
Young Chrysler Jeep Dodge Ram Morgan - 6839 | Conquest | Mid Market | Sujatha | 2025-09-02 | 2025-08-27 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Young Ford of Brigham City - 6840 | Conquest | Mid Market | Sujatha | 2025-09-02 | 2025-08-27 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Young Honda - 6837 | Conquest | Mid Market | Nanjunda | 2025-09-02 | 2025-08-20 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Young Used Center - 6836 | Conquest | Mid Market | Sujatha | 2025-09-02 | 2025-08-27 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No | Template Issue was found Templates setups were not migrated- updated manully
Burt Watson GMC, LLC - 6832 | Buy/Sell | USA East | Nanjunda | 2025-09-03 | 2025-07-31 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Courtesy Subaru - 6862 | Conquest | USA West and Central | Not configured | 2025-09-03 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Account key and SNT were not updated- Waiting for input from the dealer. It has been update later
Chuck Anderson Ford - 6831 | Conquest | USA West and Central | Not configured | 2025-09-03 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Acura of Concord - 1725 | Conquest | USA West and Central | Nanjunda | 2025-09-08 | 2025-09-04 | Yes | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | The configuration team did not work, as the data was pending. The task was later completed by the EM
Applewood Kia Langley - 5969 | Conquest | Canada | Sujatha | 2025-09-09 | 2025-09-08 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Applewood Kia Surrey - 5731 | Conquest | Canada | Sujatha | 2025-09-09 | 2025-09-08 | No | No | Copy Store | Copy | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Don Wood Chrysler Dodge Jeep - 6901 | Conquest | USA East | Sujatha | 2025-09-09 | 2025-09-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Don Wood Ford Lincoln - 6909 | Conquest | USA East | Sujatha | 2025-09-09 | 2025-09-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Don Wood Hyundai - 6892 | New Point | USA East | Sujatha | 2025-09-09 | 2025-09-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
Don Wood Toyota - 6893 | New Point | USA East | Sujatha | 2025-09-09 | 2025-09-03 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
Don Wood Chevrolet - 6891 | Conquest | USA East | Sujatha | 2025-09-09 | 2025-09-05 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Lead Sync Issue Found
Downtown Ford Sacramento - 6847 | Conquest | Mid Market | Sujatha | 2025-09-09 | 2025-08-12 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Account key and SNT were not updated- Waiting for input from the dealer. It has been update later
Jamestown Honda - 6766 | Conquest | USA East | Sujatha | 2025-09-09 | 2025-07-18 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Luv Toyota - 6764 | Conquest | USA East | Sujatha | 2025-09-09 | 2025-07-21 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Mohawk Chevrolet - 6860 | Conquest | USA East | Nanjunda | 2025-09-09 | 2025-08-07 | No | Yes | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | Account key and SNT were not updated- Waiting for input from the dealer. It has been update later
Rosen Hyundai / Genesis Algonquin - 6657 | Conquest | USA East | Sujatha | 2025-09-09 | 2025-07-09 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Rosen Hyundai Kenosha - 6658 | Conquest | USA East | Nanjunda | 2025-09-09 | 2025-07-03 | No | Yes | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Ken Garff West Valley Chrysler Dodge Jeep Ram - 6859 | Conquest | NA | Not configured | 2025-09-14 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | No Issues
Dave Kring Chevrolet Inc - 6877 | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-08-12 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
LUV Kia of Jamestown - 6765 | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-07-08 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Galleria Chevrolet - 1903 | Conquest | USA West and Central | Not configured | 2025-09-16 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Legacy Chevrolet GMC of Waxahachie - 2046 | Buy/Sell | USA West and Central | Not configured | 2025-09-16 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Principle Mississippi, Ltd - 1770 | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-09-05 | No | Yes | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Porsche Centre Langley - 6762 | Conquest | Canada | Not configured | 2025-09-16 | NA | No | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Porsche Centre Richmond - 6825 | Conquest | Canada | Nanjunda | 2025-09-16 | 2025-07-05 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Principle Volkswagen - 1771 | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-07-18 | No | Yes | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Watford Ford Lincoln - 6827 | Conquest | Canada | Nanjunda | 2025-09-16 | 2025-08-25 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Wind Gap Chevrolet - 922 | Conquest | USA East | Nanjunda | 2025-09-16 | 2025-06-25 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No | Communication template were missing in prodcution Communication templates were blown out.
Ken Garff Hyundai Downtown - 6883 | Conquest | NA | Not configured | 2025-09-21 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | No Issues
Ken Garff Hyundai Southtowne - 6907 | Conquest | NA | Not configured | 2025-09-21 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | No Issues
Daniels Chevrolet Buick GMC - 6804 | Conquest | USA East | Sujatha | 2025-09-23 | 2025-07-16 | Yes | Yes | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Oremor of Temecula LX, LLC - 1817 | Conquest | USA West and Central | Not configured | 2025-09-23 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Oremor of Temecula, LLC - 1816 | Conquest | USA West and Central | Not configured | 2025-09-23 | NA | No | NA | Config team didn’t work on the store | Not Configured | Sujatha | Yes | Yes | No Issues | Nanjunda | No Issues | No Issues | No Issues | No Issues | No Issues
Rosen Ford - 6695 | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-08 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
Rosen Honda - 6696 | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-08 | No | No | EM asked for standard Config | Stnadard Configuration | Sujatha | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
Rosen Hyundai Greenfield - 6694 | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-09 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
Rosen Kia Milwaukee - 6692 | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-15 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
Rosen Nissan Milwaukee - 6700 | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-14 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
Rosen Nissan of Madison - 6693 | Conquest | Mid Market | Nanjunda | 2025-09-23 | 2025-07-14 | No | No | EM asked for standard Config | Stnadard Configuration | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
Carvana Chrysler Dodge Jeep Ram of Park Cities - 7061 | Buy/Sell | USA West and Central | Sujatha | 2025-09-23 | 2025-09-19 | No | No | Copy store | Copy | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
Subaru of Lethbridge - 6900 | Conquest | Canada | Nanjunda | 2025-09-23 | 2025-07-21 | No | No | Copy store | Copy | Nanjunda | Yes | Yes | No Issues | Sujatha | No Issues | No Issues | No Issues | No Issues | No Issues
MAG CDJR - 6982 | Buy/Sell | USA West and Central | Not configured | 2025-09-26 | NA | NA | NA | Config team didn’t work on the store | Not Configured | Nanjunda | Yes | Yes | No Issues | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Umable to Test | Golive date moved
Carvilla - 6905 | Conquest | USA East | Nanjunda | 2025-09-29 | 2025-09-08 | No | No | EM asked for standard Config | Stnadard Configuration
Marthaler Honda - 5801 | Conquest | USA West and Central | Sujatha | 2025-09-29 | 2025-09-25 | NA | NA | EM asked for standard Config | Stnadard Configuration
Autoplex Atlanta - 6904 | Conquest | USA East | Nanjunda | 2025-09-29 | 2025-09-08 | No | No | EM asked for standard Config | Stnadard Configuration
Clark Nissan - 6560 | Conquest | USA West and Central | Sujatha | 2025-09-30 | 2025-09-15 | No | No | EM asked for standard Config | Stnadard Configuration
Community HOL Automotive, LLC - 1471 | Conquest | USA East | Sujatha | 2025-09-30 | 2025-07-03 | No | No | EM asked for standard Config | Stnadard Configuration
Diehl Chevrolet of North Hills - 7018 | Buy/Sell | USA East | Not configured | 2025-09-26 | NA | NA | NA | Config team didn’t work on the store | Not Configured
Gunther Daytona - 6879 | Conquest | USA East | Sujatha | 2025-09-30 | 2025-08-26 | No | No | Copy store | Copy
Medlin Hyundai - 2181 | Conquest | USA East | Sujatha | 2025-09-30 | 2025-07-21 | No | No | EM asked for standard Config | Stnadard Configuration
Medlin Buick GMC Mazda - 2179 | Conquest | USA East | Nanjunda | 2025-09-30 | 2025-07-18 | No | No | EM asked for standard Config | Stnadard Configuration
Neptune Motors LLC - 7055 | Buy/Sell | USA East | Not configured | 2025-09-26 | NA | NA | NA | Config team didn’t work on the store | Not Configured
Stokes Kia - 6800 | Conquest | Mid Market | Nanjunda | 2025-09-30 | 2025-09-04 | No | No | EM asked for standard Config | Stnadard Configuration

## Oct 2025
Dealership Name | Implementation Type | Region | Configuration - Assigned | Go Live Date | Date of Completion | Configuration - User List | Configuration - BP | Configuration - Comments | Configuration - Status | Pre Go Live - Assigned to | Pre Go Live - Domain Updated | Pre Go Live - Set Up Check | Pre Go Live - Comments | Go Live Testing - Assigned To | Go Live Testing - Sample ADF | Go Live Testing - Inbound Email Test | Go Live Testing - Outbound Mail Test | Go Live Testing - Data Migration Test | Go Live Testing - Comments | Config team didn’t work on the store
MAG CDJR - 6982 | Buy/Sell | USA East | Handled by EM | 2025-10-01 | [15 empty] | EM asked for standard Config
Clark Nissan - 6560 | Conquest | USA West and Central | Sujatha | 2025-10-07 | 2025-09-15 | NA | NA | EM asked for standard Config | Stnadard Configuration | [10 empty] | CRM not enabled
Eby Ford Lincoln - 6916 | Conquest | USA East | Nanjunda | 2025-10-07 | 2025-09-15 | NA | NA | EM asked for standard Config | Stnadard Configuration | [10 empty] | Copy Store
Elco Chevrolet Cadillac - 6911 | Conquest | USA West and Central | Nanjunda | 2025-10-07 | 2025-09-09 | NA | NA | EM asked for standard Config | Stnadard Configuration
Fresno Lexus - 2004 | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-07
Pine Belt CDJR, INC - 1595 | Conquest | USA West and Central | Yet to start | 2025-10-07
Pine Belt Ford - 1593 | Conquest | USA West and Central | Yet to start | 2025-10-07
Pine Belt Imports - 1596 | Conquest | USA West and Central | Yet to start | 2025-10-07
Pine Belt Imports of Brookhaven LLC - 1597 | Conquest | USA West and Central | Yet to start | 2025-10-07
Pine Belt Motors, LLC. - 1594 | Conquest | USA West and Central | Yet to start | 2025-10-07
Richmond Hill Hyundai - 1226 | Conquest | Canada | Yet to start | 2025-10-07
Thornhill Hyundai - 1126 | Conquest | Canada | Yet to start | 2025-10-07
Ken Garff Nissan of Orem - 6894 | Conquest | NA | Not Under Ready For Configuration | 2025-10-12
Ken Garff Honda of Orem - 6896 | Conquest | NA | Not Under Ready For Configuration | 2025-10-12
Ken Garff Volkswagen - 6895 | Conquest | NA | Not Under Ready For Configuration | 2025-10-12
Centennial Imports, Inc. - 1794 | Conquest | USA East | Not Under Ready For Configuration | 2025-10-13
Normandin CJDR - 1013 | Conquest | USA West and Central | Yet to start | 2025-10-13
Lexus Carlsbad - 6647 | Conquest | USA West and Central | Nanjunda | 2025-10-14 | 2025-08-04 | NA | NA | EM asked for standard Config | Stnadard Configuration
Liberty CDJR - 7010 | New Point | USA East | Yet to start | 2025-10-14
Lexus Escondido - 6646 | Conquest | USA West and Central | Nanjunda | 2025-10-14 | 2025-08-05 | NA | NA | EM asked for standard Config | Stnadard Configuration
Medlin Hyundai - 2181 | Conquest | USA East | Sujatha | 2025-10-14 | 2025-07-21 | NA | NA | EM asked for standard Config | Stnadard Configuration
Medlin Buick GMC Mazda - 2179 | Conquest | USA East | Nanjunda | 2025-10-14 | 2025-07-18 | NA | NA | EM asked for standard Config | Stnadard Configuration
Medlin Chevrolet - 2180 | Conquest | USA East | Nanjunda | 2025-10-14 | 2025-09-25 | Yes | Yes | EM asked for standard Config | Stnadard Configuration
Nordic Imports II, Ltd. - 1768 | Conquest | USA East | Yet to start | 2025-10-14
Mercedes - Benz of El Cajon - 1994 | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-14
Performance of Mt. Moriah, Ltd. - 1767 | Conquest | USA East | Yet to start | 2025-10-14
Irvine Acura - 5811 | Buy/Sell | USA West and Central | Not Under Ready For Configuration | 2025-10-14
Ineos Grenadier of Irvine - 7073 | Buy/Sell | Mid Market | Not Under Ready For Configuration | 2025-10-14
Hartwell Hereford - 6562 | Conquest | United Kingdom | Not Under Ready For Configuration | 2025-10-15
Young Chrysler Dodge Jeep of Riverdale - 7076 | Buy/Sell | Mid Market | Sujatha | 2025-10-21 | 2025-09-24 | NA | NA | Copy store | Copy
Bell and Bell Buick GMC - 6988 | Conquest | Mid Market | Nanjunda | 2025-10-21 | 2025-09-24 | Yes | Yes | EM asked for standard Config | Stnadard Configuration
Gunther Coconut Creek - 6940 | Conquest | USA East | Sujatha | 2025-10-21 | 2025-09-23 | NA | NA | Copy store | Copy
Gunther Delray Beach - 6939 | Conquest | USA East | Sujatha | 2025-10-21 | 2025-09-23 | NA | NA | Copy store | Copy
Larson Cadillac - 6724 | New Point | Mid Market | Sujatha | 2025-10-21 | 2025-06-10 | NA | NA | EM asked for standard Config | Stnadard Configuration
Larson Dodge - 6723 | New Point | Mid Market | Sujatha | 2025-10-21 | 2025-06-13 | NA | NA | EM asked for standard Config | Stnadard Configuration
Porsche Tacoma - 6725 | New Point | Mid Market | Sujatha | 2025-10-21 | 2025-06-17 | NA | NA | EM asked for standard Config | Stnadard Configuration
Larson Hyundai of Tacoma - 6726 | New Point | Mid Market | Nanjunda | 2025-10-21 | 2025-06-09 | NA | NA | EM asked for standard Config | Stnadard Configuration
Mercedes - Benz of Tacoma - 6727 | New Point | Mid Market | Nanjunda | 2025-10-21 | 2025-06-09 | NA | NA | EM asked for standard Config | Stnadard Configuration
Volkswagen of Tacoma - 6728 | New Point | Mid Market | Nanjunda | 2025-10-21 | 2025-06-09 | NA | NA | EM asked for standard Config | Stnadard Configuration
Audi Tacoma - 6730 | Conquest | Mid Market | Nanjunda | 2025-10-21 | 2025-06-10 | NA | NA | EM asked for standard Config | Stnadard Configuration
Oremor of Tustin, LLC - 1763 | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-21
Toyota of Tacoma - 6729 | New Point | Mid Market | Nanjunda | 2025-10-21 | 2025-06-20 | NA | NA | EM asked for standard Config | Stnadard Configuration
Ken Garff Porsche Lehi - 6720 | Conquest | NA | Not Under Ready For Configuration | 2025-10-26
Ken Garff Audi Lehi - 6722 | Conquest | NA | Not Under Ready For Configuration | 2025-10-26
Paul Miller Ford, Inc. - 965 | Conquest | USA East | Not Under Ready For Configuration | 2025-10-27
Alpha One Ford - 6996 | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-28
Baker City Auto Ranch - 6974 | Conquest | Mid Market | Not Under Ready For Configuration | 2025-10-28
Community HOL Automotive, LLC - 1471 | Conquest | USA East | Sujatha | 2025-10-28 | 2025-07-03 | NA | NA | EM asked for standard Config | Stnadard Configuration
Fallon Ford - Toyota - 6746 | Conquest | USA West and Central | Not Under Ready For Configuration | 2025-10-28
Folsom Buick GMC - 6978 | Conquest | USA West and Central | Yet to start | 2025-10-28
Epic Chevrolet Cadillac - 6977 | Conquest | USA West and Central | Yet to start | 2025-10-28
Mountain Home Auto Ranch - 6976 | Conquest | Mid Market | Not Under Ready For Configuration | 2025-10-28
Stateline Auto Ranch Subaru - 6975 | Conquest | Mid Market | Not Under Ready For Configuration | 2025-10-28
Skalnek Ford - 6973 | Conquest | USA East | Not Under Ready For Configuration | 2025-10-28